## All (hidden)
Suface Pump Tests and Core Deployments | Start Tool Deployment (hh:mm)* | Start Coring (hh:mm)* | End Coring (hh:mm) | End Tool Deployment (hh:mm) | Outcome
2017-05-09
Surface Pump Test 1 PCTB-CS - bit just above sea surface below ship | 16:21 |  |  | 16:46 | Success, only small pressure differential observed across core liner.
Surface Pump Test 2 PCTB-CS - bit just above sea surface below ship | 16:53 |  |  | 17:10 | Success, only small pressure differential observed across core liner.
Surface Pump Test 3 (cement pump) PCTB-CS - bit just above sea surface below ship | 19:53 |  |  | 20:22 | Success, only small pressure differential observed across core liner.
2017-05-10
Seafloor Pump Test X (incomplete test) - bit just above seafloor | 21:10 |  |  | 22:30 | INCOMPLETE - electrical problems
Seafloor Pump Test 1 PCTB-CS - bit just above seafloor | 22:35 |  |  | 23:15 | Success, only small pressure differential observed across core liner.
Seafloor Pump Test 2 PCTB-CS w/ cement pump - bit just above seafloor | 23:15 |  |  | 0:00 | Success, only small pressure differential observed across core liner.
2017-05-11
(continued) Seafloor Pump Test 2 PCTB-CS w/ cement pump | 0:00 |  |  | 1:00 | Success, after switch to cement pump.
2017-05-12
Core UT-GOM2-1-H002-01, F/8062 T/8072 | 6:08 | 7:36 | 8:40 | 9:20 | Failed; core barrel not pressurized, pressure boost failed to fully-charge the PCTB-CS. Recovered 2.26 ft, 0 psi
PCTB-CS BHA Water Test 1 | 9:30 |  |  | 10:10 | Pressure boost failed to charge PCTB-CS autoclave.
PCTB-CS BHA Water Test 2 | 10:10 |  |  | 12:30 | Pressure boost failed to charge PCTB-CS autoclave.
Core UT-GOM2-1-H002-02, F/8072 T/8082 | 16:07 | 18:30 | 19:00 | 19:45 | Failed; ball valve did not close. Recovered 5.33 ft, 0 psi
Core UT-GOM2-1-H002-03, F/8082 T/8092 | 22:00 | 22:25 | 23:15 | 05:00 (May 13) | Failed; ball valve did not close due to use of emergency release tool. Recovered 1.08 ft, 0 psi
2017-05-13
Core UT-GOM2-1-H002-04, F/8092 T/8102 | 12:35 | 13:07 | 13:35 | 15:15 | Success; Recovered 4.6 ft, 3372 psi
Core UT-GOM2-1-H002-05, F/8102 T/8112 | 17:58 | 19:47 | 20:01 | 20:32 | Failed, core barrel not pressurized; Recovered 3.1 ft, 0 psi
2017-05-14
Core UT-GOM2-1-H002-06, F/8112 T/8122 | 0:10 | 2:15 | 2:31 | 3:00 | Failed, ball valve partially closed (not sealed), core barrel not pressurized. Silt and sand found packed between ball valve and seal; Recovered 5.2 ft, 0 psi
Core UT-GOM2-1-H002-07, F/8122 T/8132 | 7:04 | 7:27 | 8:14 | 9:03 | Failed, ball valve partially closed (not sealed), sand and silt found packed between ball valve and seal, core barrel not pressurized; Recovered 1.5 ft, 0 psi
Core UT-GOM2-1-H002-08, F/8132 T/8142 | 12:57 | 13:13 | 13:49 | 14:53 | Failed, core barrel not pressurized; Recovered 4.6 ft, 0 psi
2017-05-15
no testing or core deployments on May 15
2017-05-16
PCTB-FB BHA Water Test 3 | 6:55 |  |  | 7:55 | Failed, no pressure boost, autoclave not sealed.
PCTB-FB BHA Water Test 4 | 10:00 |  |  | 11:00 | Success
PCTB-FB BHA Water Test 5 | 14:35 |  |  | 15:30 | Success
* All time measured in UTC−5 timezone

## Flow tests
Flow Tests | Operational Depth (RKB ft) | Outcome
2017-05-09 |  |  | Shallow Flow Tests | Operational Depth (fbrf) | Outcome
Shallow Flow Test 1 PCTB-CS | 48 - 51 | Success, only small pressure differential observed across core liner. | Shallow Flow Test 1 PCTB-CS | 52 | Only small pressure differential observed across core liner.
Shallow Flow Test 2 PCTB-CS | 48 - 51 | Success, only small pressure differential observed across core liner. | Shallow Flow Test 2 PCTB-CS | 52 | Only small pressure differential observed across core liner.
Shallow Flow Test 3 PCTB-CS | 48 - 51 | Success, only small pressure differential observed across core liner. | Shallow Flow Test 3 PCTB-CS w/ cement pump | 52 | Only small pressure differential observed across core liner.
2017-05-10
Deep Flow Test X PCTB-CS | 6715 - 6720 | INCOMPLETE - electrical problems
Deep Flow Test 1 PCTB-CS | 6715 - 6720 | Success, only small pressure differential observed across core liner. | Deep Flow Tests | Operational Depth (fbrf) | Outcome
Deep Flow Test 2 PCTB-CS w/ cement pump | 6715 - 6720 | Success, only small pressure differential observed across core liner. | Deep Flow Test X PCTB-CS | 6715 - 6720 | INCOMPLETE - electrical problems
|  |  | Deep Flow Test 1 PCTB-CS | 6715 - 6720 | Only small pressure differential observed across core liner.
|  |  | Deep Flow Test 2 PCTB-CS w/ cement pump | 6715 - 6720 | Only small pressure differential observed across core liner.

## Full-Function
Full Function Tests | Operational Depth (RKB ft) | Outcome
2017-05-12 |  |  | Full Function Tests | Operational depth (fbrf) | Outcome
PCTB-CS Full-Function Test 1 | 8072 | Pressure boost failed to charge PCTB-CS autoclave. | PCTB-CS Full-Function Test 1 | 8072 | Pressure boost failed to charge PCTB-CS autoclave.
PCTB-CS Full-Function Test 2 | 8072 | Pressure boost failed to charge PCTB-CS autoclave. | PCTB-CS Full-Function Test 2 | 8072 | Pressure boost and seal occurred, however the middle section had lower pressure due to a hydraulic lock.