## Actual Time Line
UT/DOE GOM^2 Marine Test Daily Log
Revision: 0 Date: 6 June 2017
Date | Time | Activity Description | Daily Log
2017-04-20 |  | UT representative arrives at Keppel AmFELS Shipyard in Brownsville, TX. | Shipyard work continued on the vessel (Q4000) in dry dock. Tom Pettigrew (Pettigrew Engineering/UT), Quentin Huggett (Geotek), Sally Huggett (Geotek, not sailing), Mike Mimitz (Geotek), Allan Bakken (Geotek), and Matt Selman (Geotek) arrived at the Kepple AmFELS shipyard in Brownsville, Texas. A shipyard briefing was given and then identification and gangway passes were issued. Vish Subramani (Helix) escorted the group to the Q4000 where a shipboard safety briefing was given as well as a tour of the vessel. Positions for the Geotek PCATS containers were laid out on deck. Electrical and air connections were located. Water connections are yet to be defined. Required lengths of utility hoses and cables was measured. The rig floor was inspected as well as the mouse hole locations, tuggers, etc. While sitting on the dock, the PCTB service van was opened and inspected, all was found to be as shipped. The DNV frame was located in another part of the shipyard and requested to be moved dockside.
2017-04-21 |  | Q4000 in dry dock, shipyard work continues. | Shipyard work continued on the vessel in dry dock. No shipments were received.
2017-04-22 |  | PCATS, PCTB, BHA components arrive dockside in Brownsville, TX | Shipyard work continued on the vessel in dry dock. All of the Geotek Pressure Core Analysis and Transfer System (PCATS) containers and all three lifting baskets, one from Austin and two from Houston arrived and were offloaded from their trucks to dockside. Helix requested a change in the PCATS container layout on deck. Geotek personnel boarded the Q4000 to confer on the changes.
2017-04-23 |  | Chillers, cold shuck arrive dockside in Brownsville, TX, chillers installed in DNV frame. | Shipyard work continued on the vessel in dry dock. Lifting basket contents were inventoried and required tubulars and subs were present. The chillers arrived late afternoon and were offload from the truck dockside.
2017-04-24 |  | Q4000 moved out of dry dock and tied up dockside. | Shipyard work continued on the vessel in dry dock. The chillers were installed in the DNV frame. Nitrogen bottles were secured in a rack. The revised deck layout for the PCATS containers was approved by both Helix and Geotek. At 0930 hrs. the dry dock began flooding in preparations for moving the Q4000 alongside the dock. The Q4000 was tied up dockside at 1700 hrs.
2017-04-25 |  | Q4000 shipyard work continues. | Shipyard work continued on the vessel dock side. Loading of the Geotek and UT equipment was discussed with Rig Superintendent.
2017-04-26 |  | Q4000 shipyard work continues. | Shipyard work continued on the vessel dock side.
2017-04-27 |  | Q4000 shipyard work continues. | Shipyard work continued on the vessel dock side. All Geotek personnel completed the SafeGulf course. Peter Polito (University of Texas at Austin (UT)), Steve Phillips (UT), Kevin Meazell (UT), and Tiannong Dong (UT) arrived.
2017-04-28 |  | Q4000 shipyard work continues. | Shipyard work continued on the vessel dock side. Additional UT personnel that arrived Thursday were given the shipyard safety briefing and issued identification and gangway passes. Peter Flemings (UT) arrived.
2017-04-29 |  | UT personnel board Q4000. | Shipyard work continued on the vessel dock side. Peter Flemings was given the shipyard safety briefing and issued identification and a gangway pass. All Geotek PCATS containers were loaded on board and positioned on deck. The lifting baskets from Houston were unloaded dockside and the contents loaded onboard the Q4000. All UT personnel move on board the Q4000 at 1600 hrs. and given the shipboard safety briefing.
2017-04-30 |  | Geotek personnel board Q4000. | UT and Geotek staff boarded the Q4000. All Geotek containers were loaded onto the vessel. Phone and internet connected to company man and the 3rd party offices. Representatives from UT, Geotek, Helix, Schlumberger, and Weatherford met to discuss the status/plans for rig floor and container operations going forward. These plans include utility connections to Geotek containers, grating installation, Schlumberger wireline rig up through the top drive, Weatherford instrumentation, and mouse-hole installation/modification. The current priority is for Helix to finish loading and load-testing before the above operations can continue.
2017-05-01 | 0750 | Begin transit to FMEA site. | At 0750hr the Q4000 left the dock at Brownsville, TX and was guided by the harbor pilot through the channel towards South Padre Island. At 1020hr the vessel entered the Gulf of Mexico, and continued offshore at 1105hr after the pilot disembarked. At 1300hr conducted fire drill. Geotek Coring gained access to clean freshwater for their core lab containers. Helix began required vessel sea trials by 2200hr.
| 2200 | Arrive FMEA site.
2017-05-02 |  | Conduct sea trials, FMEA. | Helix continued to conduct required vessel sea trials. Geotek-Coring continued to prepare core lab containers (PCATS) for operations.
Assemble and test PCATS.
2017-05-03 |  | Conduct sea trials, FMEA. | Helix continued to conduct required vessel sea trials. Geotek-Coring continued to prepare core lab containers (PCATS) for operations.
Assemble and test PCATS.
2017-05-04 | 1800 | 1 nmi off FMEA site, begin transit and lump sum mobilization. | Helix completed a crew change through the morning and afternoon with three helicopter flights. After transfers were complete, the Q4000 was de-ballasted and began to transit towards GC955. Helix began installing the grating around Geotek-Coring (PCATS) containers. Geotek-Coring continued to prepare core lab containers (PCATS) for operations.
Rig Movement Notification submitted.
Geotek continued to organize and inventory their equipment.
2017-05-05 |  | Underway for H002 site. | The Q4000 continued transit towards GC955 throughout the day. Grating was installed around Geotek Coring (PCATS) containers. UT, Helix, Geotek-Coring and all third parties participated in a pre-spud meeting to discuss the expedition objectives and the operational plan. Schlumberger and Helix worked on rigging up the wireline equipment through the top drive.
Pre-spud meeting held.
Grating installed around Geotek’s containers.
Geotek continuing to set up their equipment.
Rig up wireline equipment to/through top drive.
2017-05-06 | 1600 | 1 nmi off operations site. | The Q4000 arrived within 1 nmi of location of the GC955-H001 well at 1600hr after a 307 nmi transit. Schlumberger and Helix complete the rigging up the wireline equipment through the top drive. Geotek-Coring continued to prepare Geotek Coring (PCATS) containers and PCTB pressure core systems. The ROV was launched at 2040he to deploy four Compact transponders and survey the site area. The GC955-H001 well was found at 2247hr at a location of 27° 00.05126’ N, 090° 25.58367’ W in a WGS84 coordinate system. The borehole well head at the seafloor was intact and in good condition.
Geotek continued to prepare their equipment.
Launch ROV, deploy transponders, conduct as-found survey.
Locate Hole H001 at 27° 00.05126’ N, 090° 25.58367’ W (WGS84).
2017-05-07 | 0230 | M/V HOS Crockett arrived on site with equipment and mud from Fourchon, LA, begin offload. | Helix conducted a partial crew change via three helicopter flights. The supply boat M/V HOS Crockett was offloaded over most of the day; drilling mud, gel, and the mud lab were brought on board. The as-found ROV survey of the seafloor was completed. Geotek-Coring conducted trial PCTB core system runs in the Geotek Coring (PCATS) labs. Helix worked on installing the HVAC system for the mud pumps. Weatherford installed a new interface and software to monitor and record drilling and coring parameters.
Crew change occurred via three helicopter flights.
Mud lab offloaded.
Completed as-found survey with the ROV.
Weatherford installed interface and software to record drilling parameters.
2017-05-08 | 1227 | The M/V HOS Crockett departed. | Conducted fire/abandon ship drill at 0819hr. The supply boat M/V HOS Crockett materials transfer was completed and departed at 1227hr. The UT mud lab was placed into location on the deck of the Q4000 and hooked up to utilities. Helix finished installing the duct work for the mud pumps. Made up ~2300 ft of drill pipe between 1400-1930hr and then between 1940-2200hr pilled up and laid down pipe in doubles. Starting at 2015hr, Weatherford software began logging top drive data; allowing for the recording of all drilling parameters, except the stroke counter on the mud pumps. Helix performed pressure testing of the upper and lower IBOP valves and the wireline night cap starting at 2315hr.
Spot mud lab, connect utilities.
| 1400-2200 | Make up ~2300 ft of drill pipe and lay out in doubles.
| 2315 | Begin pressure testing upper and lower IBOP valves and wireline night cap.
2017-05-09 | 0800 | Complete pressure testing upper and lower IBOP valves and wireline night cap. | Conducted a series of three Shallow Flow Tests of the PCTB-CS pressure core system with the BHA hanging just below the sea surface. Preliminary analysis of data from Geotek instrumented core liner shows only small pressure differentials across the core liner during each of the three Shallow Flow Tests of the PCTB-CS. The instrumented core liner upon visual inspection did not exhibit any damage or deformation. The PCTB-CS Surface Pump Test revealed a potential problem associated with the use of the shipboard Hex mud pumps in that the pumps could not effectively work below a flow rate of about 125 GPM. It has been shown in the past that high mudflow rates, exceeding about 30 GPM, can cause severe borehole washouts and adversely affect core recovery. A decision was made to also test the use of the Schlumberger cement pumps to determine if lower mud pump rates could be established and maintained. As shown above, the cement pumps used during Surface Pump Test 3 was able to establish and maintain low flow rates in the range of 21-40 GPM. The current operational plan has been modified to include the use of the onboard cement pumps during planned pressure coring operations. There were three helicopter flights for crew change, and the remainder of the UT Science Party arrived at 1445hr and went through the safety orientation.
| 0800 | MU PCTB-CS OCBA for flow test.
| 1145 | UT personnel board via helicopter from Houma, LA.
| 1230-1300 | Space out with PCTB and instrumented core barrel
| 1621-1646 hr | Surface Pump Test 1 PCTB-CS
| 1653-1710 hr | Surface Pump Test 2 PCTB-CS
| 1953-2022 hr | Surface Pump Test 3 (cement pump) PCTB-CS
| 2130-2400 | Space out cementing liner, center bit and PCTB-CS.
2017-05-10 | 0000-0215 | MU PCTB-CS BHA. | Made-up and ran to the seafloor the BHA with drill collars and pipe reaching near the seafloor (̴6716 ft MD) at 2110hr and the Geotek instrumented core barrel was deployed in preparation for conducting a series of seafloor level flow tests. The first attempted Deep Flow Test was not completed because of an electrical problem associated with one of the ship’s mud pumps. However, two additional seafloor pump tests were completed without any concerns. The flow tests also allowed for the analysis of the performance of all three pump units on the platform (i.e., Hex Pumps 1 and 2; and the Schlumberger cement pump). Analysis of data obtained from both the sea surface and seafloor flow tests documented only small pressure differentials across the core liner for all of the completed tests. In addition, the instrumented core liner was not damaged during any of the completed pump test. Modifications to the drilling fluid flow paths through the PCTB-CS appear to have significantly reduced the internal pressure conditions that have in the past resulted in the collapse of core liners within the PCTB-CS system. The pump tests also represented an excellent opportunity for Geotek-Coring and the Q4000 rig crew to become more familiar with operations and handling of the PCTB-CS pressure core system as deployed on this expedition.
| 0215-1630 | RIH w/ bit on drill pipe.
| 1630-1930 | Change bails on TDS, stage PCTB-CS, RU wireline.
| 1930-2110 | RIH w/ instrumented core barrel.
| 2110-2230 | Seafloor Pump Test X PCTB-CS (incomplete test)
Using Hex Pump 2 switched to Hex Pump 1 (circulating seawater)
| 2230-2315 | Seafloor Pump Test 1 PCTB-CS
| 2315-2400 | Seafloor Pump Test 2 (cement pump) PCTB-CS
| 0912-1647 | USCG inspection.
2017-05-11 | 0000-0100 | Complete Seafloor Pump Test 2 (cement pump) PCTB-CS | At 0830hr spudded Hole UT-GOM2-1-H002 at 6667.0 ft (6719.0 ft RKB) and advanced hole to a depth of 8032.0 ft RKB (1313.0 fbsf) by midnight without any significant problems. Geotek-Coring completed preparations for coring operations and developed plans for simulated core runs to be conducted before reaching core point as planned for the morning of 12-May-17. The UT Scientific Party refined and finalized the Hole UT-GOM2-1-H002 core plan. The UT Scientific Party also continued to develop the core handling and processing plan. Based on (1) lateral correlation with seismic data from Hole GC955-H as drilled under the Gulf of Mexico Gas Hydrate Joint Industry Project Leg II (GOM JIP Leg II) in 2009 to the Hole UT-GOM2-1-H002 and (2) the seafloor depth at UT-GOM2-1-H002, the first pressure core point (Core UT-GOM2-1-H002-01) was set at 8062.0 ft RKB (1343.0 fbsf).
| 0100-0500 | POOH w/ instrumented core barrel.
RIH w/ center bit.
| 0500-0530 | Test wireline night cap on TDS to 5000 psi
| 0530-0600 | Held Spud meeting with all personnel involved
| 0600-0830 | RIH w/ bit.
| 0630-0730 | Move rig over H002 location.
| 0730-0830 | Tag mudline at 6719.0 ft.
| 0830-2300 | Spud Hole H002.
Drill 6719.0 ft to 8032.0 ft.
| 0856-1215 | BSEE inspection (Inspectors Campo, Boudreaux, Fry, Shedd)
| 2300-2400 | Circulate hole clean with 8.6 ppg mud
2017-05-12 | 0000-0030 | Fill hole w/ 10.5 ppg WBM. | Performed a series of three simulated coring drill downs with the bit just off the bottom of the hole. Hole UT-GOM2-1-H002 was advanced from 8062 ft MD to 8092 ft MD with 3 PCTB-CS pressure cores (Core UT-GOM2-1-H002-01-CS, Core UT-GOM2-1-H002-02-CS, and Core UT-GOM2-1-H002-02-CS). Conducted core run: Core UT-GOM2-1-H002-01CS. Core barrel recovered on deck with ball valve closed but with little to no pressure in the autoclave. Core UT-GOM2-1-H002-01CS, which was the first core acquired during this expedition, recovered 2.3 ft (69 cm) of core in poor condition and failed to retain pressure. The deployment, cutting, and recovery of the core appeared to be conducted without any problems. We did not see any trouble with the latching of the tool or it's deployment in the pipe. But it took more than 6,000 lbs of pull to unlatch the tool from the BHA. The cutting of the core on bottom also appeared to be good with somewhat variable penetration rates and weight on bit. Upon recovery, the ball valve was closed but the pressure boost appeared not to have pressurized the autoclave below the new flow diverter set above the upper autoclave seal (polypack seals). Two additional PCTB-CS operational tests were conducted in the open drillpipe (while not in contact with the sediment) that appeared to confirm that there was some form of pressure block in the tool. Conducted core run: Core UT-GOM2-1-H002-02CS. When the tool was recovered on deck the ball valve was not closed; core liner visible through ball valve (no pressure). Core did not retract into the autoclave. The upper threaded connection of the liner to the top of the core plug was broken and the core catcher was damage indicating that the core likely jammed, which caused core milling and the breaking of the liner. It also took about a 6000 lb pull to unlatch the inner core barrel from with the BHA during the recovery of the core. A total of 5.3 ft (162 cm) of sediment was recovered. Conducted core run: Core UT-GOM2-1-H002-03CS. Upon recovery this core failed to hold pressure; however, it did return core to the surface. This failure of the core system to retain pressure was attributed to the fact that the retrieval of the inner core-barrel required a special procedure to release it form the latches in the BHA. We did not see any trouble with the deployment and latching of the tool before coring. The actual core cut event appeared to be good with somewhat variable penetration rates and weight on bit. However, at the end of the test the inner core-barrel was stuck in the BHA. The rig crew and Geotek staff core team managers worked with the Schlumberger wireline engineer for nearly four hours to unlatch the core barrel from the BHA. Eventually, the decision was made to use a special emergency release procedure that was successful but also prevents the ball-valve on the tool from closing. A total of 1.1 ft (33 cm) was recovered. The ‘conventionalized’ core material from each core was transferred to the UT mud lab whole rounds were subsampled and preserved for shore-based geochemistry, microbiology, and physical properties. Head space gas samples were sampled for shore-based analyses.
| 0030-0230 | Performed coring simulations drilling down: 8032 ft - 8042 ft, 8042 ft - 8052 ft, 8052 ft - 8062 ft.
| 0230-0330 | Circulate hole clean.
| 0330-0730 | POOH w/ center bit.
RIH w/ PCTB-CS.
| 0730-0900 | Core H002-01, F/ 8062 ft T/ 8072 ft.
| 0900-0930 | POOH w/ PCTB-CS (recovered 2.3 ft, 0 psi).
| 0930-1010 | RIH w/ PCTB-CS for water core test 1.
POOH PCTB-CS (0 psi, boost failed).
| 1010-1230 | RIH w/ PCTB-CS for water core test 2.
POOH w/ PCTB-CS (0 psi, boost failed).
| 1230-1830 | RIH w/ PCTB-CS.
Circulate hole clean.
| 1830-1900 | Core H002-02, F/ 8072 ft T/ 8082 ft.
| 1900-1945 | POOH w/ PCTB-CS (recovered 5.3 ft, 0 psi) (liner did not retract preventing ball valve from closing.
| 1945-2230 | RIH w/ PCTB-CS.
Circulate hole clean.
| 2230-2330 | Core H002-03, F/ 8082 ft T/ 8092 ft.
| 2330-2400 | RIH w/ pulling tool.
2017-05-13 | 0000-0400 | PCTB-CS would not unlatch from the BHA. | Hole UT-GOM2-1-H002 was advanced from 8092 ft MD to 8112 ft MD with 2 PCTB-CS pressure cores (Core UT-GOM2-1-H002-04CS and Core UT-GOM2-1-H002-05CS). Conducted core run: Core UT-GOM2-1-H002-04CS. Core UT-GOM2-1-H002-04CS was recovered on deck with ball valve closed and at an internal autoclave pressure of 3372 psi, which was the first core acquired during this expedition at pressure. The deployment and recovery of the PCTB-CS core barrel was conducted without any problems. The cutting of the core at the bottom of the hole also appeared to be good with almost constant core penetration rates and weight on bit. Upon recovery, the PCTB-CS core barrel was placed in the vertical ice-shuck on the rig floor. The internal pressure of the PCTB-CS autoclave when received in the Geotech Coring Service Van measured 3372 psi, which is slightly less than the expected hydrostatic pressure at the depth of the cored reservoir section at this site. In the PCATS lab, an X-ray scan of the PCTB-CS autoclave revealed 4.6 ft (140 cm) section of sediment core and 4.0 ft (123 cm) sediment fill above the core rabbit, which indicates that formation sediment had been fluidized during coring and flowed up into the core liner through the small ports in the rabbit. Conducted core run: Core UT-GOM2-1-H002-05CS. For Core UT-GOM2-1-H002-05, the ball-valve failed to close or hold pressure; however, it did return core to the surface. For Core UT-GOM2-1-H002-05CS the tool was recovered to the rig floor with the ball-valve closed but not sealed. Silt and sand was found packed between the ball valve and seal; and the seal appeared to be damaged. We also had significant trouble unlatching this tool from the BHA during recovery, which may also have been caused by the impact of silt/sand on the operation of the latch system within the PCTB-CS BHA. Core UT-GOM2-1-H002-05CS did recover 3.1 ft (94 cm) of non-pressurized core that was transferred and processed through the onboard UT core processing lab.
Pumped numerous mud sweeps and worked SLB slickline.
POOH w/ pulling tool, RIH w/ emergency pulling tool.
| 0345 | POOH w/ PCTB-CS (recovered 1.1 ft, 0 psi).
| 0400-0630 | RIH w/ PCTB-CS.
| 0630-0900 | Pulling tool shear released PCTB.
POOH w/ pulling tool, RIH w/ emergency pulling tool.
POOH w/ PCTB-CS.
| 0900-1300 | RIH w/ PCTB-CS.
| 1300-1330 | Core H002-04, F/ 8092 ft T/ 8102 ft. MD: Recovered 4.6 ft, 3372 psi
| 1330-1530 | POOH w/ PCTB-CS (recovered 4.6 ft, 3372 psi)
| 1530-1930 | RIH w/ PCTB-CS.
| 1930-2000 | Core H002-05, F/ 8102 ft T/ 8112 ft. MD: Recovered 3.1 ft, 0 psi
| 2000-2400 | POOH w/ PCTB-CS (recovered 3.1 ft, 0 psi)
| 0540-1130 | M/V Mr Steven arrive/departed location.
2017-05-14 | 0000-0200 | RIH w/ PCTB-CS. | Hole UT-GOM2-1-H002 was advanced from 8112 ft RKB to 8142 ft RKB with 3 PCTB-CS pressure cores (Core UT-GOM2-1-H002-06CS, Core UT-GOM2-1-H002-07CS, Core UT-GOM2-1-H002-08CS). All three of the recovered PCTB-CS cores failed to hold pressure. Conducted core run: Core UT-GOM2-1-H002-06CS. For Core UT-GOM2-1-H002-06CS, the ball-valve closed, seal at top end of autoclave plug failed; however, it did return core to the surface. For Core UT-GOM2-1-H002-06 the tool was recovered to the rig floor with the ball-valve partially closed (not sealed). Silt and sand was found packed between the ball valve and seal. Core UT-GOM2-1-H002-06 recovered 5.2 ft (158 cm) of non-pressurized core that was transferred and processed through the onboard UT core processing lab. Conducted core run: Core UT-GOM2-1-H002-07CS. For Core UT-GOM2-1-H002-07CS, the ball-valve failed to close or hold pressure (displaced BV seal); however, it did return core to the surface. For Core UT-GOM2-1-H002-07 the tool was recovered to the rig floor with the ball-valve partially closed (not sealed). Silt and sand was found packed between the ball valve and seal. In addition, sediment was also found above the core rabbit in the PCTB-CS autoclave, indicating that formation sediment had been fluidized during coring and flowed up into the core liner through the small ports in the rabbit. Core UT-GOM2-1-H002-07 did recover 1.5 ft (46 cm) of non-pressurized core that was transferred and processed through the onboard UT core processing lab. Conducted core run: Core UT-GOM2-1-H002-08CS. For Core UT-GOM2-1-H002-08CS, the ball-valve failed to actuate or hold pressure. The ball-valve release sleeve (collett) failed by sliding over stop position, which resulted in the failure of the ball-valve to actuate. Core UT-GOM2-1-H002-08 did recover 4.6 ft (140 cm) of non-pressurized core that was transferred and processed through the onboard UT core processing lab. Hole UT-GOM2-1-H002 reached a TD of 8142 ft RKB (1423 fbsf) at 1630 hr with the recovery of Core UT-GOM2-1-H002-08, after which the hole was swept with 280 bbls of 10.5 ppg water-based mud in preparation for downhole wireline logging. The wireline logging tool string (including EDTC-HRLA-GPIT) was lowered to bottom of the hole, and two up hole log runs from 8045 ft RKB to 7680 ft RKB (Main Pass and Repeat Pass) were acquired without any problems. Because of borehole blockages, the wireline logging tool string could not pass below 8045 ft RKB and the BHA had been set back to a depth of 7680 ft RKB. Wireline Logs: EDTC-HRLA-GPIT F/7680 ft RKB T/8045 ft RKB (Main Pass) Wireline Logs: EDTC-HRLA-GPIT F/7680 ft RKB T/8045 ft RKB (Repeat Pass)
| 0200-0230 | Core H002-06, F/ 8112 ft T/ 8122 ft. MD: Recovered 5.2 ft, 0 psi
| 0230-0315 | POOH w/ PCTB-CS (recovered 5.2 ft, 0 psi).
| 0315-0730 | RIH w/ PCTB-CS.
| 0730-0830 | Core H002-07, F/ 8122 ft T/ 8132 ft. MD: Recovered 1.5 ft, 0 psi
| 0830-0920 | POOH w/ PCTB-CS (recovered 1.5 ft, 0 psi).
| 0920-1330 | RIH w/ PCTB-CS.
| 1330-1400 | Core H002-08, F/ 8132 ft T/ 8142 ft.
| 1400-1530 | POOH w/ PCTB-CS (recovered 4.6 ft, 0 psi) (ball valve did not actuate).
| 1530-1630 | Decision made to TD Hole H002 at 8142 ft.
Pumped 280 bbls of 10.5 ppg to sweep hole clean.
| 1630-1730 | Rig up logging sheaves.
| 1730-1830 | POOH w/ bit F/ 8142 ft T/ 7680 ft.
| 1830-2040 | RU logging wireline through travel block and TDS
MU logging wireline packoff in TD
Terminate logging wireline cable head
MU logging tool string.
| 2040-2400 | RIH w/ EDTC-HRLA-GPIT (logging tool string includes Induction Inclinometer).
Unable to pass 8045 ft.
Log up F/ 8045 ft T/ 7680 ft.
RIH w/ EDTC-HRLA-GPIT F/ 7680 ft T/ 8045 ft.
Log up F/ 8045 ft T/ 7680 ft.
Continue up hole log run to obtain seafloor log depth at 6704 ft.
POOH w/ logging tool string.
2017-05-15 | 0000-0130 | Continue POOH w/ logging tool string. | Logging program in Hole UT-GOM2-1-H002 was completed with the acquisition of a main pass and repeat pass surveys (EDTC-HRLA-GPIT) over the depth interval from 7680 ft RKB to 8045 ft RKB. Hole UT-GOM2-1-H002 was abandoned with the emplacement of a 500 ft cement plug that was set above the hydrate interval to avoid any potential problem associated with hydrate dissociation that may be caused by the heat generated by cement hydration. The last half of the day dealt with preparations to move onto the location of Hole UT-GOM2-1-H005. Prepared and set cement plug in Hole UT-GOM2-1-H002 from a depth of 7900 ft RKB to 7400 ft RKB. Recovered PCTB-CS BHA to the ship and prepared to run the PCTB-FB version of the PCTB pressure core system.
RD logging tools, wireline, and wireline sheaves
| 0130-0430 | RIH w/ bit F/ 7680 ft T/ 8142 ft.
Spot 25 bbls 11.5 ppg Gel pad mud.
POOH w/ bit BHA F/ 8142 ft T/ 7900 ft.
Pump 200 bbls of 10.5 ppg WBM.
Drop cementing liner.
| 0430-1230 | Pump 17 bbls gel spacer.
Drop Nerf ball, pump 3 bbls of 10.5 ppg spacer.
Pump 77 bbls 16.4 ppg cement.
Pump 17 bbls of gel spacer.
Displace drill string w/ 171 bbls of seawater.
POOH w/ bit F/ 7900 ft T/ 6611 ft.
Flush drill string w/ 350 bbls seawater and 2 nerf balls.
POOH w/ cementing liner.
Flush DS w/ 245 bbls of seawater.
| 1230-1825 | POOH w/ bit
BO BHA (5 drill collars, 2 stabilizers, bit sub, bit) inspect for residual cement.
| 1825-2400 | MU face bit OCBA.
Space out center bit, PCTB-FB, cementing liner.
| 2132 | M/V Gerry Bordelon on location.
2017-05-16 | 0000-0330 | Complete space out center bit, PCTB-FB, cementing liner. | Conducted three full function (water) tool tests of the PCTB-FB in the drill pipe as it was being deployed in preparation for drilling the next test hole in the project (Hole UT-GOM2-1-H005). To further test the engineering capability of the “face-bit” version of the PCTB pressure-coring tool, it was tested in three successive tests in which the configuration of the tool was not changed between each tests and the coring and core handling procedures were conducted in a similar fashion in each test. The tools as tested were all the face-bit cutting version of the PCTB, which is also known as the PCTB-FB. In each case the “flow diverter” in the pressure core barrel was sealed with an O-ring. These tests were all full function tests in that the PCTB-FB inner barrel was lowered into drill pipe on a slick line wire, (2) the PCTB-FB inner barrel was locked into the BHA, (3) the wireline “running in” tool was used to deploy the PCTB-FB inner barrel and the wireline “pulling” tool was used to recover the PCTB-FB inner barrel to the deck of the ship. Under normal operations, the pulling tool is deployed and latches into the PCTB-FB inner barrel in the BHA and when pulled by the slick line the ball-valve at the bottom of the PCTB-FB inner barrel closes, the upper valve on the tool closes, the entire inner core barrel unlatches from the BHA, and the onboard pressure boost system activates to maintain internal tool pressures during recovery.
| 0210 | Begin transferring 881 bbls 16.0 ppg WBM from M/V Gerry Bordelon.
| 0719 | M/V Gerry Bordelon depart location.
| 0330-0800 | MU PCTB-FB BHA
RIH w/ bit T/ 1090 ft.
| 0800-1000 | RIH w/ PCTB-FB for water core test 3.
Circulate seawater at 2 bpm using Hex Pump 2
POOH w/ PCTB-FB.
| 1000-1200 | RIH w/PCTB-FB for water core test 4.
Circulate seawater at 2 bpm using Hex Pump 2
POOH w/ PCTB-FB.
| 1200-1630 | RIH w/ PCTB-FB for water core test 5.
Circulate seawater at 1.75 bpm using Hex Pump 2
POOH w/ PCTB-FB.
| 1630-1800 | RIH w/ center bit.
| 1800-2400 | RIH w/ bit F/ 1090 ft T/ 6700 (18 ft above sea floor).
Backload equipment to M/V Gerry Bordelon.
2017-05-17 | 0000-0124 | Move rig over Hole H002. | Re-entered Hole UT-GOM2-1-H002 to tag and test cement plug, tagged top of cement plug at 6839 ft RKB. Set down 11000lbs on top of cement plug. D/S Q4000 was moved over proposed location of Hole UT-GOM2-1-H005. Hole UT-GOM2-1-H005 was spud at 6666.0 ft (6718.0 ft RKB) at 0230hr and advanced to the first core point at 7645 ft RKB. Acquired pressure core from a known fracture dominated hydrate-bearing section that overlies the hydrate-bearing sand-rich reservoir section that is the primary coring target at the Green Canyon 955 test site. Conducted core run: Core UT-GOM2-1-H005-01FB. The core throw for the 01 core was 10ft, but from drilling performance data it appeared that the core only cut about 5-6 ft of formation. On recovery, the ball valve was closed and the autoclave was conditioned in the cold shuck for 20 minutes before a pressure of 4115 psi was measured in the service van, indicating that the pressure boost had been retained. The autoclave was moved to PCATS for core handling and processing. The target depth for Core UT-GOM2-1-H005-01 was specifically selected to test the impact of mud-rich sediments on the PCTB-FB core system. A total of 7.1 ft (217 cm) of sediment was recovered.
Reenter Hole H002.
RIH w/ bit, tag top of cement at 6839 ft, apply 11,000 lb WOB.
POOH w/ bit F/ 6839 ft T/ 6690 ft.
Weekly activity report end submitted.
| 0124-0230 | Move rig over proposed Hole H005 location.
RIH w/ bit, tag mudline at 6718.0 ft.
| 0230-1330 | Spud Hole H005.
Drill to 7654 ft.
| 1330-2230 | POOH w/ center bit.
RIH w/ PCTB-FB.
PCTB-FB failed to land in BHA.
POOH w/PCTB-FB.
RIH w/ PCTB-FB.
| 2230-2330 | Core H005-01, F/ 7645 ft T/ 7655 ft.
POOH w/ PCTB-FB (recovered 7.1 ft, 4115 psi).
| 2330-2400 | RIH w/ center bit.
2017-05-18 | 0000-0625 | Drill F/ 7655 ft T/ 8081 ft, w/ seawater and Hi vis sweeps every 2 doubles. | Continued drilling Hole UT-GOM2-1-H005 from 7655 ft RKB to 8081 ft RKB the depth of the next core point in the hole. Acquired and logged in PCATS Core UT-GOM2-1-H005-02FB and Core UT-GOM2-1-H005-03FB. These scans indicated high P-wave velocities consistent with hydrate at high-saturations. Conducted core run: Core UT-GOM2-1-H005-02FB. Successful coring run with clean pick up from BHA. On recovery the ball valve was closed and the autoclave was left in the cold shuck for 45 mins before a pressure of 2834 psi was measured in the service van, indicating that there was a very slight leak which was located around the ball valve. The autoclave pressure was increased to 4000 psi before being transferred to PCATS. A total of 4.9 ft (150 cm) of sediment was recovered. Conducted core run: Core UT-GOM2-1-H005-03FB. Another good coring run with clean pick up from BHA. On recovery the ball valve was closed and the autoclave was left in the cold shuck for 45 mins before a pressure of 1780 psi was measured in the service van indicating that there might be a slow leak. The autoclave was transferred to PCATS where pressure was increased to 4000 psi before core handling and processing. DST record showed that autoclave had fully sealed during recovery. A total of 10.0 ft (304 cm) of sediment was recovered.
| 0625-1130 | POOH w/ center bit.
| 1130-1200 | RIH w/ PCTB-FB.
| 1200-1240 | Core H005-02, F/ 8081 ft T/ 8091 ft.
POOH w/ PCTB-FB (recovered 4.9 ft, 2834 psi).
| 1240-1545 | RIH w/ PCTB-FB.
Tag fill at 8086 ft.
POOH w/ PCTB-FB.
| 1545-1700 | Pump 25 bbls gel sweep followed by 280 bbls seawater.
| 1700-1930 | RIH with core barrel.
| 1930-2120 | Core H005-03, F/ 8091 ft T/ 8101 ft.
POOH w/ PCTB-FB (recovered 10 ft, 1780 psi).
| 2120-2230 | Circulated 25 bbls gel sweep followed by 128 bbls seawater.
| 2230-2400 | Prepare to take core UT-GOM2-1-H005-04
2017-05-19 | 0000-0130 | RIH w/ PCTB-FB. | Advanced Hole UT-GOM2-1-H005 from 8101 ft RKB to 8151 ft RKB with the acquisition of five pressure cores. Conducted core run: Core UT-GOM2-1-H005-04FB. On recovery the ball valve was closed and the autoclave was left in the cold shuck for 43 mins before a pressure of 3477 psi was measured in the service van indicating that the autoclave had sealed at in situ pressures. The autoclave was transferred to PCATS for core handling and processing. DST record showed that autoclave had fully sealed as it was lifted from the BHA. Core recovery 10.5 ft (321 cm) as measured by X-ray image in PCATS. Conducted core run: Core UT-GOM2-1-H005-05FB. On recovery the ball valve was closed and the autoclave was left in the cold shuck for 35 mins before a pressure of 3242 psi was measured in the service van indicating that the autoclave had sealed around the in situ pressure. The autoclave was transferred to PCATS for core handling and processing. Core recovery was 9.7 ft (296 cm) as measured by X-ray image in PCATS. Conducted core run: Core UT-GOM2-1-H005-06FB. Good coring run with clean pick up from BHA and a sea floor ‘cooling stop’ for 15 mins. On recovery the ball valve was closed and the autoclave was left in the cold shuck for 35 mins before a pressure of 3250 psi was measured in the service van indicating that the autoclave had sealed around the in situ pressure. The autoclave was transferred to PCATS for core handling and processing. Core recovery was 9.4 ft (286 cm) as measured by X-ray image in PCATS. Conducted core run: Core UT-GOM2-1-H005-07FB. Good coring run with clean pick up from BHA and a sea floor ‘cooling stop’ for 15 mins. On recovery the ball valve was closed and the autoclave was left in the cold shuck for 46 mins before a pressure of 3164 psi was measured in the service van indicating that the autoclave had sealed around the in situ pressure. The set pressure for this deployment was made at 3000 psi and consequently there was no boost. The autoclave was transferred to PCATS for core handling and processing. Core recovery was 10.5 ft (321 cm) as measured by X-ray image in PCATS. Conducted core run: Core UT-GOM2-1-H005-08FB. Switched from drilling with seawater to drilling with 9.5 lb/gal mud. Good coring run but the pick up from BHA took multiple efforts before it cane free. The tool was stopped at the sea floor (cooling stop) for 15 mins. On recovery the ball valve was closed and the autoclave was left in the cold shuck for 77 mins before a pressure of 3016 psi was measured in the service van indicating that the autoclave had sealed around the set pressure indicating that the accumulator boost may have assisted sealing the autoclave. The autoclave was transferred to PCATS for core handling and processing. Core recovery was 8.2 ft (250 cm) as measured by X-ray image in PCATS.
| 0130-0330 | Core H005-04, F/ 8101 ft T/ 8111 ft.
POOH w/ PCTB-FB (recovered 10.5 ft, 3477 psi).
| 0330-0400 | Gel sweep followed by seawater.
| 0400-0630 | RIH w/ PCTB-FB.
| 0630-0800 | Core H005-05, F/ 8111 ft T/ 8121 ft.
POOH w/ PCTB-FB (recovered 9.7 ft, 3242 psi).
| 0800-0900 | Gel sweep followed by seawater
| 0900-1100 | RIH w/ PCTB-FB.
| 1100-1230 | Core H005-06, F/ 8121 ft T/ 8131 ft.
POOH w/ PCTB-FB (recovered 9.4 ft, 3250 psi).
| 1230-1300 | Gel sweep followed by seawater
| 1300-1500 | RIH w/ PCTB-FB.
| 1500-1700 | Core H005-07, F/ 8131 ft T/ 8141 ft.
POOH w/ PCTB-FB (recovered 10.5 ft, 3164 psi).
| 1700-1830 | Displaced hole w/ 9.5 ppg WBM, begin pump and dump w/ 9.5 ppg WBM.
| 1830-2000 | RIH w/ PCTB-FB.
| 2000-2400 | Core H005-08, F/ 8141 ft T/ 8151 ft.
POOH w/ PCTB-FB (recovered 8.2 ft, 3016 psi).
2017-05-20 | 0000-0230 | Re-headed slick line. | Advanced Hole UT-GOM2-1-H005 from 8151 ft RKB to 8185 ft RKB with the acquisition of four pressure cores. Conducted core run: Core UT-GOM2-1-H005-09FB. Good coring run with a clean pick-up from the BHA with a 15 minutes autoclave cooling stop at the sea bed to experiment with further cooling of the autoclave. On recovery the ball valve was closed and the autoclave was left in the cold shuck for 55 minutes before a pressure of only 746 psi was measured in the service van. On this occasion the set pressure was 4015 psi and hence the boost did not function as expected and there was no accumulator function. The pressure was pumped up to 3250 psi before being transferred to PCATS. The DST recordings showed that autoclave did not seal until it close at the surface and was probably aided by at least partial dissociation of gas hydrates. Core recovery was 8.9 ft (270 cm) as measured by the X-ray image in PCATS (includes a number of voids). Conducted core run: Core UT-GOM2-1-H005-10FB. During the coring the cement pumps (mud pumps) stopped temporarily (~30 sec). At approximately 5 ft into formation bit reached very high torque (as much as 30 klbs) and released, causing the drill string to spin in reverse momentarily. Coring was discontinued immediately at this point. On recovery, the ball valve was closed but there was an indication there may be a slight leak (which proved to be wrong) and hence the tool was moved quickly out of the cold shuck to the service van where the pressure was found to be 3255 psi. It was then placed in the cold bath before being transferred to PCATS. A total of 1.4 ft (44 cm) of sediment was recovered. Conducted core run: Core UT-GOM2-1-H005-11FB. After the difficulties experienced during the last coring run, the main objective of Core UT-GOM2-1-H005-11FB was to advance through what is interpreted on the logs as a water bearing zone before another short gas hydrate interval beneath it. Consequently the pump rates were increased significantly at the expense of the core quality to ensure that a clean hole was developed for the next core (Core UT-GOM2-1-H005-12FB) which is back in a gas hydrate interval. The tool was deployed in the BHA before a core was cut using the 10.5 lb/gal mud. After picking up from BHA and retrieving to the rig floor the ball valve was closed and the autoclave was left in the cold shuck for 45 minutes before a pressure of 3002 psi was measured in the service van. The autoclave was placed in the cold bath while PCATS was being prepared. A total of 0.9 ft (26 cm) of sediment was recovered. Conducted core run: Core UT-GOM2-1-H005-12FB. The tool was deployed in the BHA before a core was cut using the 10.5 lb/gal mud. Weight and torque came on bit 1 ft early (above core point) hence the run was stopped after a 9 ft advance. Generally a good coring run with clean a pick up from BHA, however on recovery the ball valve was only half closed trapping sediment in the ball follower and hence having zero pressure. Core barrel was over-filled, with rabbit against top plug and core material across the ball valve. Recovery was 5.4 ft (165 cm).
RIH w/ PCTB-FB.
| 0230-0630 | Core H005-09, F/ 8151 ft T/ 8161 ft.
POOH w/ PCTB-FB (recovered 8.9 ft, 746 psi).
Fill/sweep hole with 10.5 ppg mud, begin pump and dump w/ 10.5 ppg WBM.
| 0630-1030 | RIH w/ PCTB-FB.
Failed to latch in BHA.
POOH w/ PCTB-FB, remove broken latch pin.
RIH w/ PCTB-FB.
| 1030-1200 | Core H005-010, F/ 8161 ft T/ 8166 ft.
POOH w/ PCTB-FB (recovered 1.4 ft, 3255 psi).
Sweep hole with 10.5 ppg mud.
| 1501-1811 | M/V Mr Steven arrive/departed location.
| 1200-1600 | RIH w/ PCTB-FB.
| 1600-1730 | Core H005-011, F/ 8166 ft T/ 8176 ft.
POOH w/ PCTB-FB (recovered 0.9 ft, 3002 psi).
Sweep hole with 10.5 ppg WBM.
| 1730-2000 | RIH w/ PCTB-FB.
| 2000-2400 | Core H005-012, F/ 8176 ft T/ 8185 ft (partial core to accommodate for fill).
POOH w/ PCTB-FB (recovered 5.4 ft, 0 psi).
Sweep hole with 10.5 ppg WBM.
2017-05-21 | 0000-0030 | RIH w/ PCTB-FB. | Advanced Hole UT-GOM2-1-H005 to the total depth of the hole at 8193 ft with the acquisition of pressure core Core UT-GOM2-1-H005-13-FB. Conducted core run: Core UT-GOM2-1-H005-13FB. Before the deployment of the PCTB-FB inner core barrel, a 3/8 inch hole was drilled in the middle barrel and the set boost pressure was raised above the in situ pressure to ~4000 psi. This modification was designed to test whether the additional flow path would help create a boost pressure. Good coring run with a clean pick-up from the BHA with a 15 minutes autoclave cooling stop at the sea bed to experiment with further cooling of the autoclave. After picking up from BHA and retrieving to the rig floor the ball valve was closed and an autoclave pressure of 2806 psi was measured in the service van. The autoclave was placed in the cold bath while PCATS was being prepared. Core recovery was 5.8 ft (175 cm) as measured by the X-ray image in PCATS. Conduct two uphole directional gyroscopic surveys from the 8100 ft RKB to the seafloor. Wireline Log: Gyroscopic directional survey F/8100 ft RKB T/surface (Run-1) Wireline Log: Gyroscopic directional survey F/8100 ft RKB T/surface (Run-2) Hole UT-GOM2-1-H005 was abandoned with the emplacement of a 500 ft cement plug that was set above the hydrate interval to avoid any potential problem associated with hydrate dissociation. Prepared and set cement plug in Hole UT-GOM2-1-H005 from a depth of 7900 ft RKB to 7400 ft RKB.
| 0030-0230 | Core H005-013FB, F/ 8185 ft T/ 8193 ft (partial core to accommodate for fill).
POOH w/ PCTB-FB (recovered 5.8 ft, 2806 psi).
| 0230-0800 | RIH w/ gyroscopic survey tool.
Conduct up hole survey F/ 8100 ft T/ seafloor.
POOH w/ gyroscopic survey tool.
Review data, determine 2nd run required.
RIH w/ gyroscopic survey tool.
Conduct up hole survey F/8100 ft T/ seafloor.
POOH w/ gyroscopic survey tool.
| 0800-0930 | Spot 28 bbls 11.5 ppg high-viscosity pad mud in bottom of hole.
POOH w/ bit T/ 7900 ft.
| 0930-1230 | Pump 17 bbls of 10.5 ppg gel spacer.
BO cement head and load nerf ball.
Pump 3 bbl of 10.5 ppg spacer.
Pump 54.7 bbls of 16.4 ppg cement.
Pump 6.7 bbl of 10.5 ppg gel spacer.
Displace drill string with 180.7 bbls of seawater.
| 1230-1830 | POOH w/ bit F/ 7900 ft T/ 6600 ft.
Flush drill string w/ 350 bbls of seawater and 2 nerf balls.
Waiting on cement.
| 1830-2230 | RIH w/ bit T/ 7621 ft, unable to tag cement.
| 2230-2400 | POOH w/ bit T/ 6800 ft.
Waiting on cement
Rig Movement Notification submitted.
2017-05-22 | 0000-0900 | POOH w/ bit T/ 6600 ft (above mudline). | Re-entered Hole UT-GOM2-1-H005 to tag and test cement plug, tagged top of cement plug at 7691 ft RKB. Set down 15000lbs on top of cement plug. Began to backload project equipment to the supply vessel HOS Red Rock. Decision was made to set additional cement ontop of existing cement plug in Hole UT-GOM2-1-H005; with BHA at 1691 ft RKB, pumped 58 bbls cement slurry and bbls tail spacer.
Waiting on cement
Flush DP with 250 bbls of seawater.
| 0900-1100 | RIH w/ bit, tag top of cement at 7691 ft, apply 15,000 lbs WOB.
| 1004 | M/V Red Rock on location.
| 1100-1200 | POOH w/ bit T/ 7172 ft.
| 1200-1230 | POOH w/ bit T/ 6868 ft.
| 1230-1330 | Circulate 300 bbls 10.5 ppg WBM.
| 1330-1600 | Backload project equipment to HOS Red Rock
| 1600-1730 | RIH w/ bit T/ 7691 ft, tag cement, POOH to 7686 ft.
| 1730-2130 | Backload project equipment to HOS Red Rock
| 2130-2400 | Pump 96 bbls of 10.5 ppg WBM.
Pump 17 bbls of 10.5 ppg spacer.
Drop Nerf ball, pump 3 bbls of 10.5 ppg spacer.
Pump 58 bbls 16.4 ppg cement.
Pump 17 bbls 10.5 ppg spacer.
2017-05-23 | 0000-0100 | Continue pumping spacer. | Demobilization operations continued throughout the day with the transferee of equipment to to the supply vessel HOS Red Rock. Borehole cementing operations in Hole UT-GOM2-1-H005 was completed and the drill string was was recovered and laid down as singles.
| 0100-0345 | POOH w/ bit to 5976 ft.
Flush drill string w/ 400 bbls seawater.
| 0345-1140 | RIH w/ bit to 6674 ft.
Waiting on approval from BSEE to abandoned hole w/o tagging cement.
Transfer 340 bbls of 16.0 ppg WBM to M/V Red Rock.
Backload equipment to M/V Red Rock.
Receive approval.
| 1200-1300 | POOH w/ bit to 6100 ft laying down singles.
| 1300-1330 | WOW (lightning in area).
| 1330-2400 | POOH to BHA laying down singles.
Break down BHA.
Conduct as-left site survey w/ ROV.
2017-05-24 | 0000-1200 | Continue breaking down BHA. | Demobilization operations continued throughout the day with the transferee of equipment to to the supply vessel HOS Red Rock, which departed location 2337hr. The drill string was was recovered and laid down as singles. Geotek personnel and UT representative depart rig via helicopter. Q4000 Rig moved 1 nmi off location by midnight, end of lump sum demobilization.
Backload BHA and DP.
| 0730 | UT personnel depart rig via helicopter.
| 1200-2200 | Backload project equipment.
Recover transponders.
| 1330 | Geotek personnel and UT representative depart rig via helicopter.
| 2200-2400 | Rig 1 nmi off location, end of lump sum demobilization.
| 2337 | M/V HOS Red Rock departed location.
2017-05-25 | 0000-1230 | M/V HOS Red Rock transiting from GG955 to Port of Fourchon, LA. | In the last 24 hours, completed UT-GOM2-1 demobilization operations with the arrival and offloading of the M/V HOS Red Rock in the Port of Fourchon, LA (Intermoor facilities). The pressure core storage van was offloaded by 1500 hr. From power disconnect to power hookhoop the transfer of the pressure core sample van took only 15 minutes. Also today, the UT and Geotek technical team meant to review and finalize the pressure core-cut, sampling, and degassing plans to be conducted at the PCATS/UT labs in Fourchon.
| 1230-1300 | M/V HOS Red Rock arrives InterMoor dock/facilities.
| 1300-1500 | Offload project equipment.
PCATS system transfer, with pressure cores.
UT core processing lab transfer.
| 1500-2400 | Setup PCATS and UT core labs.
Weekly activity report submitted.
2017-05-26 | 0000-1100 | Setup PCATS and UT core labs. | Setup of Geotek and UT labs at Intermoor were completed. UT continued to work on the expedition report, planning degassing activities, and preparing to ship geochemistry and microbiology samples. Geotek began PCATS scanning and cutting of Core UT-GOM2-1-H005-10FB.
| 1100-2400 | PCATS operation.
2017-05-27 | 0000-2400 | PCATS and degassing operations. | Geotek worked on scanning and cutting of Cores UT-GOM2-1-H005-11FB and 04FB. Geotek/UT began quantitative degassing of two sections from Core UT-GOM2-1-H005-10FB.
| 1000 | Delivery of over pack container.
2017-05-28 | 0000-2400 | PCATS and degassing operations | Geotek worked on scanning and cutting of Core UT-GOM2-1-H005-4FB and Core UT-GOM2-1-H005-5FB. Geotek worked on preparing the overpack unit for the first shipment of 1.2 m storage vessels to UT. UT finished quantitative degassing of two sections from Core UT-GOM2-1-H005-10FB and began quantitative degassing of 5 sections from Core UT-GOM2-1-H005-4FB, and completed one of these sections. Gases were sampled for post-cruise analysis and the remaining sediment after degassing was processed through the mud lab.
2017-05-29 | 0000-2400 | PCATS and degassing operations | Geotek worked on scanning and cutting of Core Core UT-GOM2-1-H005-5FB. It was determined that seals need to be purchased and replaced in PCATS and PCATS operation was paused. Geotek worked on preparing the overpack unit for the first of three shipments of storage vessels to Austin. The truck arrived and began transport with an expected arrival the next day 30 May 2017. UT finished quantitative degassing of two sections from Core UT-GOM2-1-H005-4FB and continued degassing two additional sections. Gases were sampled for post-cruise analysis and remaining sediment after degassing was processed through the mud lab.
| 0000-1100 | Preparation of over pack for shipping
| 1115 | Over pack departure
| 1115-2400 | PCATS and degassing operations
2017-05-30
2017-05-31 |  | H002 and H005 end of operations reports submitted.