## PCTB Marine Test t-est
UT/DOE PCTB Marine Test Activity Forecast and Time Estimate
Revision: K Date: 1 May 2017
ITEM | ACTIVITY | TASK DESCRIPTION | TIME |  |  |  | NOTES
|  |  | (hr) | CUM | Start | Stop
2017-04-29
1 | In Port | Load PCATS and PCTB containers and connect services (electric, air, water). | 24 | 24 | 0:00 | 24:00
2 | Brownsville | Load lifting baskets, rack tubulars.
3 | Texas | Install grating.
4 |  | Install wireline unit and test loading weight bar. |  |  |  |  | Requires rigging up wireline.
5
2017-04-30
6 | In Port Brownsville | Continue port call activities. | 24 | 48 | 0:00 | 24:00
7
2017-05-01
8 | FMEA Sea Trial | Transit to deep water, continue ship refurbishment, complete inspection/FMEA. | 24 | 72 | 0:00 | 24:00 | Mobilization tasks to be completed as time, equipment and personnel availability allows.
2017-05-02
9 | FMEA Sea Trial | Continue ship refurbishment, complete inspection/FMEA. | 24 | 96 | 0:00 | 24:00 | Mobilization tasks to be completed as time, equipment and personnel availability allows.
2017-05-03
10 | FMEA Sea Trial | Continue ship refurbishment, complete inspection/FMEA. | 24 | 120 | 0:00 | 24:00 | Mobilization tasks to be completed as time, equipment and personnel availability allows.
2017-05-04
11 | FMEA Sea Trial | Continue ship refurbishment, complete inspection/FMEA. | 24 | 144 | 0:00 | 24:00 | Mobilization tasks to be completed as time, equipment and personnel availability allows.
2017-05-05
12 | FMEA Sea Trial | Complete ship refurbishment, inspection/FMEA. | 24 | 168 | 0:00 | 24:00 | Mobilization tasks to be completed as time, equipment and personnel availability allows.
2017-05-06
13 | Transit to | Set up and test PCATS. | 24 | 192 | 0:00 | 24:00
14 | Site GC-955 | Assemble and test PCTB subassemblies.
15 |  | Install instrumented core liner in PCTB.
16 |  | Make up drill pipe.
17 |  | Set up and test chillers.
2017-05-07
18 | Transit to Site GC-955 | Continue transit activities. | 24 | 216 | 0:00 | 24:00
2017-05-08
19 | Mobilization | Transfer liquid mud and bulk materials. | 24 | 240 | 0:00 | 24:00
20 | (on site) | Launch ROV, deploy beacon(s), take up station.
21 |  | Perform "as found" site survey with ROV.
22 |  | Prep for PCTB flow tests.
23 |  | Test DP system.
24 |  | Load mud van and other equipment from Fourchon.
25 |  | Embark UT personnel via helicopter.
2017-05-09
26 | Mobilization (on site) | Continue on-site mobilization activities. | 24 | 264 | 0:00 | 24:00
2017-05-10
27 | Safety | Operations safety meeting. | 0.5 | 264.5 | 24:00 | 24:30 | Start time dependent on completion of mobilization tasks.
28 | MU Cutting Shoe BHA | Install lockable float valve in 9-7/8 bit sub. | 0 | 264.5 | 24:30 | 24:30 | Geotek. Pre-install.
29 |  | Install bit seal and fish pill in 9-7/8 cutting shoe bit, MU bit to bit sub. | 0 | 264.5 | 24:30 | 24:30 | Geotek. Pre-install.
30 |  | Pick up seal bore drill collar, make up bit sub/bit subassembly to seal bore drill collar, torque all connections. | 0.5 | 265 | 24:30 | 25:00 | Helix/Geotek.
31 |  | Make up landing saver sub to seal bore drill collar. | 0.25 | 265.25 | 25:00 | 25:15 | Helix/Geotek. Install replaceable landing seat.
32 |  | Make up top sub to landing saver sub. | 0.25 | 265.5 | 25:15 | 25:30 | Helix/Geotek.
33 |  | Make up head sub to top sub. | 0.25 | 265.75 | 25:30 | 25:45 | Helix/Geotek. Install latch sleeve.
34 |  | Place cutting shoe-configured PCTB lower w/ ICL using lifting clamp and tugger; land on assembly stand over 10" mousehole | 0.25 | 266 | 25:45 | 26:00 | Helix/Geotek. May stage in 10" mouse hole.
35 |  | Pick up PCTB upper end w/tugger, make up upper end to lower end. | 0.5 | 266.5 | 26:00 | 26:30 | Helix/Geotek.
36 |  | Pick up PCTB assy using tugger, remove lower end lifting clamp, transfer into drill pipe and land upper lifting clamp on crossover sub; attach tugger to wireline running tool, insert running tool in PCTB, pick up PCTB, remove latch-lock clamp and lifting clamp, land PCTB assy in BHA | 0.5 | 267 | 26:30 | 27:00 | Helix/Geotek.
37 |  | Space out cutting shoe configured PCTB. Leave PCTB in OCB assembly after spacing out. | 2.75 | 269.75 | 27:00 | 29:45 | Geotek/Helix.
38 |  | Make up drill pipe to BHA cross over sub to head sub. | 0.25 | 270 | 29:45 | 30:00 | Helix.
39 |  | Lower outer core barrel assembly w/2 stands (doubles) 5-7/8 drill pipe, hang off at rig floor. | 0.75 | 270.75 | 30:00 | 30:45 | Helix.
40 |  | PU top drive to drill pipe. | 0.5 | 271.25 | 30:45 | 31:15 | Helix.
41 | Cutting Shoe Flow Test | Start mud pump and circulate at 25 gpm, note stand pipe pressure. | 0.25 | 271.5 | 31:15 | 31:30 | Circulate sea water. Note pressure at steady state flow. Helix/Geotek.
42 |  | Increase flow rate in 25 gpm intervals, noting stand pipe pressure for each interval, to 400+ gpm, 1,000 psi max. | 0.5 | 272 | 31:30 | 32:00 | Note pressures at steady state flows. Helix/Geotek.
43 |  | Stop mud pump, rack back top drive. | 0.5 | 272.5 | 32:00 | 32:30 | Helix. Assumes top drive parked for tripping.
44 |  | POOH with 2 stands 5-7/8 drill pipe. | 0.75 | 273.25 | 32:30 | 33:15 | Helix. Leave XO sub attached to drill pipe.
45 |  | Pick up PCTB w/tugger and wireline emergency pulling tool, install lifting clamp and latch-lock clamp on PCTB upper end, land PCTB assy on drill pipe, remove emergency pulling tool. | 0.25 | 273.5 | 33:15 | 33:30 | Geotek/Helix. May stage in 10" mouse hole.
46 |  | Pick up PCTB w/tugger, transfer to 10" mousehole, install lifting clamp on PCTB lower end, land PCTB assy on assembly stand over 10" mousehole. | 0.25 | 273.75 | 33:30 | 33:45 | Geotek/Helix. May stage in 10" mouse hole.
47 |  | Break PCTB upper end, stage in shuck. | 0.5 | 274.25 | 33:45 | 34:15
48 |  | Recover PCTB lower end w/instrumented core liner and layout w/tugger/crane to service van. | 0.5 | 274.75 | 34:15 | 34:45 | Geotek/Helix.
49 |  | Remove fish pills from instrumented core liner. | 0 | 274.75 | 34:45 | 34:45 | Perform while breaking down outer core barrel assembly.
50 |  | Break bit - do not remove, break bit sub, lay out bit sub/bit subassembly. | 0.25 | 275 | 34:45 | 35:00 | Helix.
51 |  | Remove bit, recover fish pill(s). | 0.25 | 275.25 | 35:00 | 35:15 | Geotek.
52 |  | Review flow test pressure data and size bit nozzles accordingly. | 0.75 | 276 | 35:15 | 36:00 | Geotek/UT.
53 | Safety | Operations safety meeting. | 0.5 | 276.5 | 36:00 | 36:30
54 |  | Continue review flow test pressure data and size bit nozzles accordingly. | 1.25 | 277.75 | 36:30 | 37:45 | Geotek/UT.
55 |  | Make up 9-7/8 cutting shoe bit to bit sub. | 0 | 277.75 | 37:45 | 37:45 | Geotek/Helix. Complete while reviewing flow test data.
56 | RIH for Coring | Make up bit sub/bit subassy to outer core barrel assy. | 0 | 277.75 | 37:45 | 37:45 | Helix/Geotek. Complete while reviewing flow test data.
57 |  | Torque up bit and bit sub to outer core barrel assy, land outer core barrel assy at rig floor. | 0 | 277.75 | 37:45 | 37:45 | Helix. Complete while reviewing flow test data.
58 |  | Pick up cementing barrel w/tugger, land on C-plate on crossover sub. | 0 | 277.75 | 37:45 | 37:45 | Helix/Geotek. Complete while reviewing flow test data.
59 |  | Remove lifting clamp, pull C-plate, drop cementing barrel into outer core barrel assy. | 0 | 277.75 | 37:45 | 37:45 | Helix/Geotek. Complete while reviewing flow test data.
60 |  | Check cementing barrel space out. | 0 | 277.75 | 37:45 | 37:45 | Helix/Geotek. Complete while reviewing flow test data.
61 |  | Attach running tool to tugger, insert into cementing barrel, raise cementing barrel from outer core barrel assy, attach lifting clamp, land lifting clamp on crossover sub, remove running tool, attach tugger to lifting clamp, raise and lay out w/tugger. | 0.25 | 278 | 37:45 | 38:00 | Helix/Geotek. Complete while reviewing flow test data.
62 |  | Pick up center bit w/tugger, land lifting clamp on drill pipe, attach running tool to tugger, insert running tool, raise center bit assy, remove lifting clamp, lower and land in outer core barrel assy. | 0.25 | 278.25 | 38:00 | 38:15 | Helix/Geotek. Complete while reviewing flow test data.
63 |  | Space out center bit. Leave center bit in outer core barrel assy after spaced out. | 1 | 279.25 | 38:15 | 39:15 | Helix/Geotek.
64 |  | Make up 9-7/8 stabilizer to outer core barrel assy. | 0.25 | 279.5 | 39:15 | 39:30 | Helix.
65 |  | Make up 1 ea. 8-1/2 drill collar to stabilizer. | 0.25 | 279.75 | 39:30 | 39:45 | Helix.
66 |  | MU 9-7/8 stabilizer to drill collars. | 0.25 | 280 | 39:45 | 40:00 | Helix.
67 |  | MU 4 ea. 8-1/2 drill collars to stabilizer. | 1.5 | 281.5 | 40:00 | 41:30 | Helix.
68 |  | Make up drill pipe to BHA cross over sub to drill collars. | 0.25 | 281.75 | 41:30 | 41:45 | Helix.
69 |  | RIH to 6,650 ft on 5-7/8 drill pipe. Seafloor depth = 6716 ft. | 6.25 | 288 | 41:45 | 48:00 | Helix. Note, logging tool drift test may be performed prior to RIH (reference logging tool drift test time estimate).
2017-05-11
70 | Safety | Operations safety meeting. | 0.5 | 288.5 | 48:00 | 48:30
71 |  | Continue RIH to 6,650 ft on 5-7/8 drill pipe. Seafloor depth = 6716 ft. | 1.75 | 290.25 | 48:30 | 50:15 | Helix. Note, logging tool drift test may be performed prior to RIH (reference logging tool drift test time estimate).
72 |  | Pick up top drive. | 0.5 | 290.75 | 50:15 | 50:45 | Helix. Assumes top drive parked for tripping.
73 | Spud Hole | Spud hole H-002, drill 6,716 ft to 7,760 ft. | 4.25 | 295 | 50:45 | 55:00 | Helix. Drill with sea water, pump Hi-Vis and/or weighted mud sweeps as needed. May need to begin continuous 10.5 ppg mud circulation to keep hole open. Maintain top hole integrity as much as possible.
74 | Hole Survey (Gyro Tool) | Rig up wireline. | 1 | 296 | 55:00 | 56:00 | Assumes waiver to forego survey until end of hole has been denied.
75 |  | Rig up survey tool. | 0.5 | 296.5 | 56:00 | 56:30
76 |  | RIH w/survey tool on wireline. | 0.5 | 297 | 56:30 | 57:00
77 |  | Take inclination survey, POOH w/survey tool on wireline. | 0.75 | 297.75 | 57:00 | 57:45
78 |  | Lay out survey tool. | 0.5 | 298.25 | 57:45 | 58:15
79 |  | Rig down wireline. | 1 | 299.25 | 58:15 | 59:15
80 | Drilling | Drill 7,760 - 8,064 ft. | 0.75 | 300 | 59:15 | 60:00 | Helix. Drill with sea water, pump Hi-Vis and/or weighted mud sweeps as needed. May need to begin continuous 10.5 ppg mud circulation to keep hole open. Maintain top hole integrity as much as possible.
81 | Safety | Operations safety meeting. | 0.5 | 300.5 | 60:00 | 60:30
82 | Drilling | Drill 7,760 - 8,064 ft. | 0.5 | 301 | 60:30 | 61:00 | Helix. Drill with sea water, pump Hi-Vis and/or weighted mud sweeps as needed. May need to begin continuous 10.5 ppg mud circulation to keep hole open. Maintain top hole integrity as much as possible.
83 |  | Clean and condition hole as required. Fill hole with 10.5 mud. | 1 | 302 | 61:00 | 62:00 | Helix. Maintain continuous pumping of 10.5 ppg mud while coring.
84 |  | Rig up wireline, including sinker bar and jar assemblies. | 1 | 303 | 62:00 | 63:00 | Helix/Slb.
85 |  | Break drill string, load wireline/emergency pulling tool, close drill string. | 0.25 | 303.25 | 63:00 | 63:15 | Helix/Geotek/Slb.
86 |  | RIH w/wireline at max safe speed, latch center bit, maintain circulation at 10 gpm min. | 0.75 | 304 | 63:15 | 64:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
87 |  | POOH w/center bit on wireline @ max safe speed, maintain circulation at 10 gpm min. | 0.75 | 304.75 | 64:00 | 64:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
88 |  | Break drill string, install lifting clamp on center bit, land center bit on drill pipe, unlatch wireline, change out emergency pulling tool for running tool. | 0.25 | 305 | 64:45 | 65:00 | Helix/Geotek.
89 |  | Lay out center bit w/tugger. | 0.25 | 305.25 | 65:00 | 65:15 | Helix/Geotek.
90 |  | Pick up PCTB lower end w/tugger, land lifting clamp on assembly stand over 10" mousehole. | 0.25 | 305.5 | 65:15 | 65:30 | Helix/Geotek. May stage in 10" mousehole.
91 |  | Pick up PCTB upper end w/tugger, make up to lower end, lift and transfer to drill pipe, land PCTB assy on drill pipe. | 0.5 | 306 | 65:30 | 66:00 | Helix/Geotek.
92 |  | Latch wireline to PCTB assy, pick up PCTB assy, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, land/latch PCTB in outer core barrel assy, maintain circulation at 10 gpm min. | 1 | 307 | 66:00 | 67:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
93 |  | POOH w/wireline @ max safe speed, break drill string, change out running tool for pulling tool, close drill string. | 0.75 | 307.75 | 67:00 | 67:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
94 |  | RIH with wireline at max safe speed to 7950 ft. | 0 | 307.75 | 67:45 | 67:45 | Slb. RIH while coring.
95 | Core 1CS | Core 8,064 ft to 8,074 ft. | 1 | 308.75 | 67:45 | 68:45 | Helix/Geotek. Note, top of hydrate @ 8,071 ft.
96 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 309.5 | 68:45 | 69:30 | Slb/Geotek/Helix. Rotate and manipulate as required.
97 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 309.75 | 69:30 | 69:45 | Helix/Geotek/Slb.
98 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 310 | 69:45 | 70:00 | Helix/Geotek/Slb.
99 |  | Break PCTB upper end, stage in mousehole. | 0.25 | 310.25 | 70:00 | 70:15 | Geotek/Helix.
100 |  | Pick up refurbished PCTB lower end w/tugger, load/land in assembly stand over 10" mousehole | 0.25 | 310.5 | 70:15 | 70:30 | Geotek/Helix.
101 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, transfer to drill pipe, land PCTB on drill pipe, | 0.5 | 311 | 70:30 | 71:00 | Geotek/Helix.
102 |  | Change out wireline pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 312 | 71:00 | 72:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
2017-05-12
103 | Safety | Operations safety meeting. | 0.5 | 312.5 | 72:00 | 72:30
104 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 313.25 | 72:30 | 73:15 | Slb/Geotek/Helix. Rotate and manipulate as required.
105 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 313.5 | 73:15 | 73:30 | Helix/Geotek/Slb.
106 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 313.5 | 73:30 | 73:30 | Slb. RIH while coring.
107 | Core 2CS | Core 8,074 ft to 8,084 ft. | 1 | 314.5 | 73:30 | 74:30 | Helix/Geotek.
108 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 315.25 | 74:30 | 75:15 | Slb/Geotek/Helix. Rotate and manipulate as required.
109 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 315.5 | 75:15 | 75:30 | Helix/Geotek/Slb.
110 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 315.75 | 75:30 | 75:45 | Helix/Geotek/Slb.
111 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 316.25 | 75:45 | 76:15 | Geotek/Helix.
112 |  | Pick up refurbished PCTB lower end w/tugger, load/land in assembly stand over 10" mousehole | 0.25 | 316.5 | 76:15 | 76:30 | Geotek/Helix.
113 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, land PCTB on drill pipe. | 0.5 | 317 | 76:30 | 77:00 | Geotek/Helix.
114 |  | Change out wireline pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 318 | 77:00 | 78:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
115 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 318.75 | 78:00 | 78:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
116 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 319 | 78:45 | 79:00 | Helix/Geotek/Slb.
117 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 319 | 79:00 | 79:00 | Slb. RIH while coring.
118 | Core 3CS | Core 8,084 ft to 8,094 ft. | 1 | 320 | 79:00 | 80:00
119 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 320.75 | 80:00 | 80:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
120 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 321 | 80:45 | 81:00 | Helix/Geotek/Slb.
121 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 321.25 | 81:00 | 81:15 | Helix/Geotek/Slb.
122 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 321.75 | 81:15 | 81:45 | Geotek/Helix.
123 | Hole Cleaning (if required) | Pick up center bit w/tugger, load/land center bit on drill pipe. | 0.25 | 322 | 81:45 | 82:00 | Helix/Slb/Geotek. Rotate and manipulate as required.
124 |  | Latch wireline to center bit, close drill string, RIH w/center bit on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 322.75 | 82:00 | 82:45 | Helix/Slb/Geotek. Rotate and manipulate as required.
125 |  | Land/latch center bit in outer core barrel assy, maintain circulation at 10 gpm min. | 0.75 | 323.5 | 82:45 | 83:30 | Helix/Slb/Geotek. Rotate and manipulate as required.
126 |  | POOH w/wireline @ max safe speed, maintain circulation at 10 gpm min. | 0 | 323.5 | 83:30 | 83:30 | Helix/Slb/Geotek. POOH whole cleaning hole.
127 |  | Break drill string, change out wireline running tool for emergency pulling tool, close drill string. | 0.25 | 323.75 | 83:30 | 83:45
128 |  | RIH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.25 | 324 | 83:45 | 84:00 | RIH while cleaning hole.
129 | Safety | Operations safety meeting. | 0.5 | 324.5 | 84:00 | 84:30
130 |  | Hole cleaning. | 0.75 | 325.25 | 84:30 | 85:15
131 |  | Latch center bit, POOH w/center bit on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 326 | 85:15 | 86:00 | Helix/Slb/Geotek. Rotate and manipulate as required.
132 |  | Break drill string, install lifting clamp on center bit, land center bit on drill pipe, unlatch wireline, lay out center bit w/tugger. | 0.25 | 326.25 | 86:00 | 86:15 | Helix/Slb/Geotek. Rotate and manipulate as required.
133 | Coring | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.25 | 326.5 | 86:15 | 86:30 | Geotek/Helix.
134 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, transfer and land PCTB assy on drill pipe. | 0.5 | 327 | 86:30 | 87:00 | Geotek/Helix.
135 |  | Change out wireline emergency pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 328 | 87:00 | 88:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
136 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 328.75 | 88:00 | 88:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
137 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 329 | 88:45 | 89:00 | Helix/Geotek/Slb.
138 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 329 | 89:00 | 89:00 | Slb. RIH while coring.
139 | Core 4CS | Core 8,094 ft to 8,104 ft. | 1 | 330 | 89:00 | 90:00
140 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 330.75 | 90:00 | 90:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
141 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 331 | 90:45 | 91:00 | Helix/Geotek/Slb.
142 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 331.25 | 91:00 | 91:15 | Helix/Geotek/Slb.
143 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 331.75 | 91:15 | 91:45 | Geotek/Helix.
144 |  | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.25 | 332 | 91:45 | 92:00 | Geotek/Helix.
145 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, transfer and land PCTB on drill pipe. | 0.5 | 332.5 | 92:00 | 92:30 | Geotek/Helix.
146 |  | Change out wireline pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 333.5 | 92:30 | 93:30 | Slb/Geotek/Helix. Rotate and manipulate as required.
147 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 334.25 | 93:30 | 94:15 | Slb/Geotek/Helix. Rotate and manipulate as required.
148 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 334.5 | 94:15 | 94:30 | Helix/Geotek/Slb.
149 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 334.5 | 94:30 | 94:30 | Slb. RIH while coring.
150 | Core 5CS | Core 8,104 ft to 8,114 ft. | 1 | 335.5 | 94:30 | 95:30
151 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.5 | 336 | 95:30 | 96:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
2017-05-13
152 | Safety | Operations safety meeting. | 0.5 | 336.5 | 96:00 | 96:30
153 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 336.75 | 96:30 | 96:45 | Helix/Geotek/Slb.
154 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 337 | 96:45 | 97:00 | Helix/Geotek/Slb.
155 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 337.5 | 97:00 | 97:30 | Geotek/Helix.
156 |  | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.25 | 337.75 | 97:30 | 97:45 | Geotek/Helix.
157 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, land PCTB on drill pipe. | 0.5 | 338.25 | 97:45 | 98:15 | Geotek/Helix.
158 |  | Change out wireline pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 339.25 | 98:15 | 99:15 | Slb/Geotek/Helix. Rotate and manipulate as required.
159 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 340 | 99:15 | 100:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
160 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 340.25 | 100:00 | 100:15 | Helix/Geotek/Slb.
161 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 340.25 | 100:15 | 100:15 | Slb. RIH while coring.
162 | Core 6CS | Core 8,114 ft to 8,124 ft. | 1 | 341.25 | 100:15 | 101:15
163 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 342 | 101:15 | 102:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
164 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 342.25 | 102:00 | 102:15 | Helix/Geotek/Slb.
165 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 342.5 | 102:15 | 102:30 | Helix/Geotek/Slb.
166 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 343 | 102:30 | 103:00 | Geotek/Helix.
167 | Drilling | Pick up center bit w/tugger, load/land center bit in drill pipe. | 0.25 | 343.25 | 103:00 | 103:15 | Helix/Slb/Geotek. Rotate and manipulate as required.
168 |  | Change out wireline pulling tool for running tool, latch wireline to center bit, pick up center bit, remove lifting clamp, close drill string, RIH w/center bit on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 344.25 | 103:15 | 104:15 | Helix/Slb/Geotek. Rotate and manipulate as required.
169 |  | Land/latch center bit in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0 | 344.25 | 104:15 | 104:15 | Helix/Slb/Geotek. Rotate and manipulate as required. POOH while drilling.
170 |  | Drill from 8,124 ft to 8,150 ft. | 0.75 | 345 | 104:15 | 105:00 | Helix.
171 | Hole Cleaning | Clean hole. | 1 | 346 | 105:00 | 106:00 | Helix.
172 |  | Break drill string, change out wireline running tool for emergency pulling tool, close drill string, RIH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 346.75 | 106:00 | 106:45 | Helix/Slb/Geotek. Rotate and manipulate as required.
173 |  | Latch center bit, POOH w/center bit on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 347.5 | 106:45 | 107:30 | Helix/Slb/Geotek. Rotate and manipulate as required.
174 |  | Break drill string, install lifting clamp on center bit, land center bit on drill pipe, unlatch wireline. | 0.25 | 347.75 | 107:30 | 107:45 | Helix/Slb/Geotek. Rotate and manipulate as required.
175 |  | Lay out center bit w/tugger. | 0.25 | 348 | 107:45 | 108:00
176 | Safety | Operations safety meeting. | 0.5 | 348.5 | 108:00 | 108:30
177 | Coring | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.5 | 349 | 108:30 | 109:00 | Geotek/Helix.
178 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, transfer and land PCTB assy on drill pipe. | 0.75 | 349.75 | 109:00 | 109:45 | Geotek/Helix.
179 |  | Change out wireline emergency pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 350.75 | 109:45 | 110:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
180 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 351.5 | 110:45 | 111:30 | Slb/Geotek/Helix. Rotate and manipulate as required.
181 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 351.75 | 111:30 | 111:45 | Helix/Geotek/Slb.
182 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 351.75 | 111:45 | 111:45 | Slb. RIH while coring.
183 | Core 7CS | Core 8,150 ft to 8,160 ft. | 1 | 352.75 | 111:45 | 112:45
184 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 353.5 | 112:45 | 113:30 | Slb/Geotek/Helix. Rotate and manipulate as required.
185 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 353.75 | 113:30 | 113:45 | Helix/Geotek/Slb.
186 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 354 | 113:45 | 114:00 | Helix/Geotek/Slb.
187 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 354.5 | 114:00 | 114:30 | Geotek/Helix.
188 |  | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.25 | 354.75 | 114:30 | 114:45 | Geotek/Helix.
189 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, land PCTB on drill pipe. | 0.5 | 355.25 | 114:45 | 115:15 | Geotek/Helix.
190 |  | Change out wireline pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 356.25 | 115:15 | 116:15 | Slb/Geotek/Helix. Rotate and manipulate as required.
191 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 357 | 116:15 | 117:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
192 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 357.25 | 117:00 | 117:15 | Helix/Geotek/Slb.
193 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 357.25 | 117:15 | 117:15 | Slb. RIH while coring.
194 | Core 8CS | Core 8,160 ft to 8,170 ft. | 1 | 358.25 | 117:15 | 118:15
195 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 359 | 118:15 | 119:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
196 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 359.25 | 119:00 | 119:15 | Helix/Geotek/Slb.
197 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 359.5 | 119:15 | 119:30 | Helix/Geotek/Slb.
198 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 360 | 119:30 | 120:00 | Geotek/Helix.
2017-05-14
199 | Safety | Operations safety meeting. | 0.5 | 360.5 | 120:00 | 120:30
200 |  | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.5 | 361 | 120:30 | 121:00 | Geotek/Helix.
201 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, land PCTB on drill pipe. | 0.5 | 361.5 | 121:00 | 121:30 | Geotek/Helix.
202 |  | Change out wireline pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.5 | 362 | 121:30 | 122:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
203 |  | Continue RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.5 | 362.5 | 122:00 | 122:30 | Slb/Geotek/Helix. Rotate and manipulate as required.
204 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 363.25 | 122:30 | 123:15 | Slb/Geotek/Helix. Rotate and manipulate as required.
205 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 363.5 | 123:15 | 123:30 | Helix/Geotek/Slb.
206 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 363.5 | 123:30 | 123:30 | Slb. RIH while coring.
207 | Core 9CS | Core 8,170 ft to 8,180 ft. | 1 | 364.5 | 123:30 | 124:30
208 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 365.25 | 124:30 | 125:15 | Slb/Geotek/Helix. Rotate and manipulate as required.
209 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 365.5 | 125:15 | 125:30 | Helix/Geotek/Slb.
210 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 365.75 | 125:30 | 125:45 | Helix/Geotek/Slb.
211 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 366.25 | 125:45 | 126:15 | Geotek/Helix.
212 |  | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.25 | 366.5 | 126:15 | 126:30 | Geotek/Helix.
213 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, land PCTB on drill pipe. | 0.5 | 367 | 126:30 | 127:00 | Geotek/Helix.
214 |  | Change out wireline pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 368 | 127:00 | 128:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
215 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 368.75 | 128:00 | 128:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
216 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 369 | 128:45 | 129:00 | Helix/Geotek/Slb.
217 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 369 | 129:00 | 129:00 | Slb. RIH while coring.
218 | Core 10CS | Core 8,180 ft to 8,190 ft. | 1 | 370 | 129:00 | 130:00 | Bottom of hydrate @ 8,166 ft RKB (1,445 fbsf).
219 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 370.75 | 130:00 | 130:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
220 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 371 | 130:45 | 131:00 | Helix/Geotek/Slb.
221 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 371.25 | 131:00 | 131:15 | Helix/Geotek/Slb.
222 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 371.75 | 131:15 | 131:45 | Geotek/Helix.
223 | Drilling | Pick up center bit w/tugger, load/land center bit in drill pipe. | 0.25 | 372 | 131:45 | 132:00 | Helix/Slb/Geotek. Rotate and manipulate as required.
224 | Safety | Operations safety meeting. | 0.5 | 372.5 | 132:00 | 132:30
225 |  | Change out wireline pulling tool for running tool, latch wireline to center bit, pick up center bit, remove lifting clamp, close drill string, RIH w/center bit on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.5 | 373 | 132:30 | 133:00 | Helix/Slb/Geotek. Rotate and manipulate as required.
226 |  | Continue RIH w/center bit on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.5 | 373.5 | 133:00 | 133:30 | Helix/Slb/Geotek. Rotate and manipulate as required.
227 |  | Land/latch center bit in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 374.5 | 133:30 | 134:30 | Helix/Slb/Geotek. Rotate and manipulate as required. POOH while drilling.
228 |  | Rig down wireline. | 1 | 375.5 | 134:30 | 135:30
229 |  | Drill 8,190 ft to 8,440 ft. | 1 | 376.5 | 135:30 | 136:30 | 250 ft rat hole for logging
230 |  | Clean hole for logging. | 1 | 377.5 | 136:30 | 137:30
231 |  | Rig up wireline. | 1 | 378.5 | 137:30 | 138:30
232 |  | RIH w/emergency pulling tool on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 379.25 | 138:30 | 139:15
233 |  | Latch center bit, POOH w/center bit on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 380 | 139:15 | 140:00 | Helix/Slb/Geotek. Rotate and manipulate as required.
234 |  | Break drill string, install lifting clamp on center bit, land center bit on drill pipe, unlatch wireline. | 0.25 | 380.25 | 140:00 | 140:15 | Helix/Slb/Geotek. Rotate and manipulate as required.
235 |  | Lay out center bit w/tugger, close drill string. | 0.25 | 380.5 | 140:15 | 140:30
236 |  | Rig down wireline. | 1 | 381.5 | 140:30 | 141:30
237 |  | POOH w/bit to 7,871 ft. | 1 | 382.5 | 141:30 | 142:30
238 | Logging | EDTC/HLDS/DSI/HRLA, Speed = 1,200 ft/hr |  | 382.5 | 142:30 | 142:30
239 |  | Rig up logging line. | 1.5 | 384 | 142:30 | 144:00
2017-05-15
240 | Safety | Operations safety meeting. | 0.5 | 384.5 | 144:00 | 144:30
241 |  | Continue to rig up logging line. | 0.5 | 385 | 144:30 | 145:00
242 |  | Rig up tool string. | 1 | 386 | 145:00 | 146:00
243 |  | Calibration before run (in pipe). | 0.25 | 386.25 | 146:00 | 146:15
244 |  | Run tool to pipe depth. | 1.25 | 387.5 | 146:15 | 147:30
245 |  | Log down. | 0.25 | 387.75 | 147:30 | 147:45
246 |  | Log up. | 0.5 | 388.25 | 147:45 | 148:15
247 |  | Log down. | 0.25 | 388.5 | 148:15 | 148:30
248 |  | Log up. | 0.5 | 389 | 148:30 | 149:00
249 |  | Log to mudline. | 1 | 390 | 149:00 | 150:00
250 |  | POOH. | 1.25 | 391.25 | 150:00 | 151:15
251 |  | Calibration after run (in pipe). | 0.25 | 391.5 | 151:15 | 151:30
252 |  | Rig down tool string. | 0.75 | 392.25 | 151:30 | 152:15
253 |  | Rig down logging line. | 2.25 | 394.5 | 152:15 | 154:30
254 | Cementing | RIH to TD @ 8,441 fbsf. | 1 | 395.5 | 154:30 | 155:30
255 |  | Displace hole from TD to 7,900 ft with 11.5 ppg Hi- Vis pad mud. | 1 | 396.5 | 155:30 | 156:30
256 | Safety | Operations safety meeting. | 0.5 | 397 | 156:30 | 157:00
257 |  | POOH to 7,900 ft. | 0.75 | 397.75 | 157:00 | 157:45 | Bit at top of pad mud, 100 ft above hydrate zone.
258 |  | Drop outer core barrel assembly (OCBA) cementing liner. | 0.75 | 398.5 | 157:45 | 158:30 | Free fall deploy.
259 |  | Pump cement per Schlumberger program. | 5 | 403.5 | 158:30 | 163:30 | 300 ft plug.
260 |  | POOH to 6,616 ft (100 ft above sea floor). | 2.5 | 406 | 163:30 | 166:00 | 100 ft above sea floor. Pull slowly through cement column 5 min/double.
261 |  | Circulate ≥2X drill string volume w/sea water and 3x rubber balls at ≥5 bbl/min. | 0.75 | 406.75 | 166:00 | 166:45 | Pump foam pipe wipers.
262 |  | Rig up wireline. | 1 | 407.75 | 166:45 | 167:45
263 |  | RIH w/pulling tool on wireline, latch OCBA cementing liner, maintain 10 gpm min circulation. | 0.25 | 408 | 167:45 | 168:00 | Circulate.
2017-05-16
264 | Safety | Operations safety meeting. | 0.5 | 408.5 | 168:00 | 168:30
265 |  | Continue RIH w/pulling tool on wireline, latch OCBA cementing liner, maintain 10 gpm min circulation. | 0.5 | 409 | 168:30 | 169:00 | Circulate.
266 |  | POOH w/OCBA cementing liner, maintain 10 gpm min circulation. | 0.75 | 409.75 | 169:00 | 169:45 | Circulate.
267 |  | Break drill string, install lifting clamp on OCBA cementing liner, land OCBA cementing liner on drill pipe, unlatch wireline. | 0.25 | 410 | 169:45 | 170:00 | Helix/Slb/Geotek. Rotate and manipulate as required.
268 |  | Lay out OCBA cementing liner w/tugger, close drill string. | 0.5 | 410.5 | 170:00 | 170:30
269 |  | Rig down wireline. | 1 | 411.5 | 170:30 | 171:30
270 |  | Circulate ≥1X drill string volume w/sea water at ≥5 bbl/min. | 0 | 411.5 | 171:30 | 171:30 | Circulate while rigging down wireline.
271 |  | Rack back top drive. | 0.5 | 412 | 171:30 | 172:00
272 | POOH | POOH to top of outer core barrel assy. | 8 | 420 | 172:00 | 180:00
273 |  | Observe borehole for signs of out flow. | 0 | 420 | 180:00 | 180:00 | Observe while cleaning drill string
274 | Safety | Operations safety meeting. | 0.5 | 420.5 | 180:00 | 180:30
275 |  | POOH to bit, break bit - do not remove - break bit sub. | 0.25 | 420.75 | 180:30 | 180:45
276 |  | Lay out bit sub/bit subassembly. | 0.25 | 421 | 180:45 | 181:00
277 |  | Remove 9-7/8 cutting shoe bit, bit seal, LFV. | 0.5 | 421.5 | 181:00 | 181:30 | Inspect for retained cement.
278 |  | Clear rig floor and stage face bit BHA components. | 1 | 422.5 | 181:30 | 182:30
279 |  | Continue to clear rig floor and stage face bit BHA components. | 1 | 423.5 | 182:30 | 183:30
280 | MU Face Bit BHA | Install standard float valve in 9-7/8 bit sub. | 0 | 423.5 | 183:30 | 183:30 | Geotek. Pre-install.
281 |  | Install bit seal and fish pill in 9-7/8 face bit, MU bit to bit sub. | 0 | 423.5 | 183:30 | 183:30 | Geotek. Pre-install.
282 |  | Pick up seal bore drill collar, make up bit sub/bit subassembly to seal bore drill collar, torque all connections. | 0.5 | 424 | 183:30 | 184:00 | Helix/Geotek.
283 |  | Make up landing saver sub to seal bore drill collar. | 0.25 | 424.25 | 184:00 | 184:15 | Helix/Geotek. Install replaceable landing seat.
284 |  | Make up top sub to landing saver sub. | 0.25 | 424.5 | 184:15 | 184:30 | Helix/Geotek.
285 |  | Make up head sub to top sub. | 0.25 | 424.75 | 184:30 | 184:45 | Helix/Geotek. Install latch sleeve.
286 |  | Pick up face bit configured PCTB lower end w/ instrumented core liner w/tugger, load/land PCTB lower end in mousehole. | 0.25 | 425 | 184:45 | 185:00 | Helix/Geotek. May stage in 10" mouse hole.
287 |  | Pick up PCTB upper end w/tugger, make up upper end to lower end. | 0.5 | 425.5 | 185:00 | 185:30 | Helix/Geotek.
288 |  | Pick up PCTB assy w/tugger, remove lower end lifting clamp, land PCTB assy on Outer Core Barrel assy. | 0.25 | 425.75 | 185:30 | 185:45 | Helix/Geotek.
289 |  | Space out face bit configured PCTB. Leave PCTB in OCB assembly after spacing out. | 2 | 427.75 | 185:45 | 187:45 | Geotek/Helix.
290 |  | Make up drill pipe to BHA cross over sub to head sub. | 0.25 | 428 | 187:45 | 188:00 | Helix.
291 |  | Lower outer core barrel assembly w/2 stands (doubles) 5-7/8 drill pipe, hang off at rig floor. | 0.75 | 428.75 | 188:00 | 188:45 | Helix.
292 |  | Make up top drive to drill pipe. | 0.5 | 429.25 | 188:45 | 189:15 | Helix.
293 | Face Bit Flow Test | Start mud pump and circulate at 25 gpm, note stand pipe pressure. | 0.25 | 429.5 | 189:15 | 189:30 | Circulate sea water. Note pressure at steady state flow. Helix/Geotek.
294 |  | Increase flow rate in 25 gpm intervals, noting stand pipe pressure for each interval, to 400+ gpm, 1,000 psi max. | 0.5 | 430 | 189:30 | 190:00 | Note pressures at steady state flows. Helix/Geotek.
295 |  | Stop mud pump, park top drive. | 0.25 | 430.25 | 190:00 | 190:15 | Helix. Assumes top drive parked for tripping.
296 |  | POOH with 2 stands 5-7/8 drill pipe. | 0.5 | 430.75 | 190:15 | 190:45 | Helix.
297 |  | Break and lay out drill pipe to BHA XO. | 0.25 | 431 | 190:45 | 191:00 | Helix. XO sub can be left on last joint of drill pipe.
298 |  | Pick up PCTB w/tugger and wireline pulling tool, install lifting clamp on PCTB upper end, land PCTB assy on outer core barrel assy, remove wireline pulling tool. | 0.25 | 431.25 | 191:00 | 191:15 | Geotek/Helix. May stage in 10" mouse hole.
299 |  | Pick up PCTB w/tugger, install lifting clamp on PCTB lower end, land PCTB assy on outer core barrel assy. | 0.25 | 431.5 | 191:15 | 191:30 | Geotek/Helix. May stage in 10" mouse hole.
300 |  | Break PCTB upper end, stage in shuck. | 0.5 | 432 | 191:30 | 192:00
2017-05-17
301 | Safety | Operations safety meeting. | 0.5 | 432.5 | 192:00 | 192:30
302 |  | Recover PCTB lower end w/instrumented core liner and layout w/tugger/crane to service van. | 0.5 | 433 | 192:30 | 193:00 | Geotek/Helix.
303 |  | Break bit - do not remove, break bit sub, lay out bit sub/bit subassembly. | 0.25 | 433.25 | 193:00 | 193:15 | Helix.
304 |  | Remove bit, recover fish pill(s). | 0.25 | 433.5 | 193:15 | 193:30 | Geotek.
305 |  | Review flow test pressure data and size bit nozzles accordingly. | 1 | 434.5 | 193:30 | 194:30 | Geotek/UT.
306 |  | Continue to review flow test pressure data and size bit nozzles accordingly. | 1 | 435.5 | 194:30 | 195:30 | Geotek/UT.
307 |  | Make up 9-7/8 face bit to bit sub. | 0 | 435.5 | 195:30 | 195:30 | Geotek/Helix. Complete while reviewing flow test data.
308 | RIH for Coring | Make up bit sub/bit subassy to outer core barrel assy. | 0 | 435.5 | 195:30 | 195:30 | Helix/Geotek. Complete while reviewing flow test data.
309 |  | Torque up bit and bit sub to outer core barrel assy, land outer core barrel assy at rig floor. | 0 | 435.5 | 195:30 | 195:30 | Helix. Complete while reviewing flow test data.
310 |  | Attach running tool to tugger, pick up cementing barrel w/tugger/running tool, remove lifting clamp, land cementing barrel in outer core barrel assy. | 0 | 435.5 | 195:30 | 195:30 | Helix/Geotek. Complete while reviewing flow test data.
311 |  | Check cementing barrel space out. | 0 | 435.5 | 195:30 | 195:30 | Helix/Geotek. Complete while reviewing flow test data.
312 |  | Remove cementing barrel from outer core barrel assy and lay out w/tugger. | 0 | 435.5 | 195:30 | 195:30 | Helix/Geotek. Complete while reviewing flow test data.
313 |  | Pick up center bit w/tugger and land in outer core barrel assy. | 0.25 | 435.75 | 195:30 | 195:45 | Helix/Geotek.
314 |  | Space out center bit. Leave center bit in outer core barrel assy after spaced out. | 1 | 436.75 | 195:45 | 196:45 | Helix/Geotek.
315 |  | Make up 9-7/8 stabilizer to outer core barrel assy. | 0.25 | 437 | 196:45 | 197:00 | Helix.
316 |  | Make up 1 ea. 8-1/2 drill collar to stabilizer. | 0.25 | 437.25 | 197:00 | 197:15 | Helix.
317 |  | MU 9-7/8 stabilizer to drill collars. | 0.25 | 437.5 | 197:15 | 197:30 | Helix.
318 |  | MU 4 ea. 8-1/2 drill collars to stabilizer. | 1.5 | 439 | 197:30 | 199:00 | Helix.
319 |  | Make up drill pipe to BHA cross over sub to drill collars. | 0.25 | 439.25 | 199:00 | 199:15 | Helix.
320 |  | RIH to 6,700 ft on 5-7/8 drill pipe. Seafloor depth = 6,716 ft. | 4.75 | 444 | 199:15 | 204:00
321 | Safety | Operations safety meeting. | 0.5 | 444.5 | 204:00 | 204:30
322 |  | Continue RIH to 6,700 ft on 5-7/8 drill pipe. Seafloor depth = 6,716 ft. | 3.25 | 447.75 | 204:30 | 207:45
323 |  | Pick up top drive. | 0.25 | 448 | 207:45 | 208:00 | Helix. Assumes top drive parked for tripping.
324 |  | Reenter Hole H-002 | 1 | 449 | 208:00 | 209:00
325 |  | RIH to 7600 ft (top of cement), set 15,000 WOB on cement. | 2 | 451 | 209:00 | 211:00 | Rotate only enough to monitor torque.
326 |  | POOH to 6625 ft (100 ft above seafloor) | 2 | 453 | 211:00 | 213:00
327 |  | Offset rig to Hole H-005 | 2 | 455 | 213:00 | 215:00
328 | Spud Hole | Spud Hole H-005, drill 6,725 ft to 7,765 ft. | 0.25 | 455.25 | 215:00 | 215:15 | Helix. Drill with sea water, pump Hi-Vis and/or weighted mud sweeps as needed. May need to begin continuous 10.5 ppg mud circulation to keep hole open. Maintain top hole integrity as much as possible.
329 | Hole Survey (Gyro Tool) | Rig up wireline. | 0.75 | 456 | 215:15 | 216:00 | Assumes waiver to forego survey until end of hole has been denied.
2017-05-18
330 | Safety | Operations safety meeting. | 0.5 | 456.5 | 216:00 | 216:30
331 |  | Continue rig up wireline. | 0.5 | 457 | 216:30 | 217:00 | Assumes waiver to forego survey until end of hole has been denied.
332 |  | Rig up survey tool. | 0.5 | 457.5 | 217:00 | 217:30
333 |  | RIH w/survey tool on wireline. | 0.5 | 458 | 217:30 | 218:00
334 |  | Take inclination survey, POOH w/survey tool on wireline. | 0.75 | 458.75 | 218:00 | 218:45
335 |  | Lay out survey tool. | 0.5 | 459.25 | 218:45 | 219:15
336 |  | Rig down wireline. | 1 | 460.25 | 219:15 | 220:15
337 | Drilling | Drill 7,765 ft to 8,063 ft. | 2 | 462.25 | 220:15 | 222:15 | Helix. Drill with sea water, pump Hi-Vis and/or weighted mud sweeps as needed. May need to begin continuous 10.5 ppg mud circulation to keep hole open. Maintain top hole integrity as much as possible.
338 |  | Clean and condition hole as required. Fill hole with 10.5 mud. | 1 | 463.25 | 222:15 | 223:15 | Helix. Maintain continuous pumping of 10.5 ppg mud while coring.
339 |  | Rig up wireline. | 1 | 464.25 | 223:15 | 224:15
340 |  | Break drill string, load wireline/pulling tool, close drill string. | 0.25 | 464.5 | 224:15 | 224:30
341 |  | RIH w/wireline at max safe speed, latch center bit, maintain circulation at 10 gpm min. | 0.75 | 465.25 | 224:30 | 225:15 | Slb/Geotek/Helix. Rotate and manipulate as required.
342 |  | POOH w/center bit on wireline @ max safe speed, maintain circulation at 10 gpm min. | 0.75 | 466 | 225:15 | 226:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
343 |  | Break drill string, install lifting clamp on center bit, land center bit on drill pipe, unlatch wireline, change out pulling tool for running tool. | 0.25 | 466.25 | 226:00 | 226:15 | Helix/Geotek.
344 |  | Lay out center bit w/tugger. | 0.25 | 466.5 | 226:15 | 226:30 | Helix/Geotek.
345 | Coring | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.25 | 466.75 | 226:30 | 226:45 | Geotek/Helix.
346 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, transfer and land PCTB assy on drill pipe. | 0.5 | 467.25 | 226:45 | 227:15 | Geotek/Helix.
347 |  | Change out wireline emergency pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 468 | 227:15 | 228:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
348 | Safety | Operations safety meeting. | 0.5 | 468.5 | 228:00 | 228:30
349 |  | POOH w/wireline @ max safe speed, break drill string, change out running tool for pulling tool, close drill string. | 0.25 | 468.75 | 228:30 | 228:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
350 |  | Continue to POOH w/wireline @ max safe speed, break drill string, change out running tool for pulling tool, close drill string. | 0.5 | 469.25 | 228:45 | 229:15 | Slb/Geotek/Helix. Rotate and manipulate as required.
351 |  | RIH with wireline at max safe speed to 7950 ft. | 0 | 469.25 | 229:15 | 229:15 | Slb. RIH while coring.
352 | Core 11FB | Core 8,063 ft to 8,073 ft. | 1 | 470.25 | 229:15 | 230:15 | Helix/Geotek. Note, top of hydrate @ 8,071 ft.
353 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 471 | 230:15 | 231:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
354 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 471.25 | 231:00 | 231:15 | Helix/Geotek/Slb.
355 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 471.5 | 231:15 | 231:30 | Helix/Geotek/Slb.
356 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 472 | 231:30 | 232:00 | Geotek/Helix.
357 |  | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.25 | 472.25 | 232:00 | 232:15 | Geotek/Helix.
358 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, land PCTB on drill pipe. | 0.5 | 472.75 | 232:15 | 232:45 | Geotek/Helix.
359 |  | Change out wireline pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 473.75 | 232:45 | 233:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
360 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 474.5 | 233:45 | 234:30 | Slb/Geotek/Helix. Rotate and manipulate as required.
361 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 474.75 | 234:30 | 234:45 | Helix/Geotek/Slb.
362 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 474.75 | 234:45 | 234:45 | Slb. RIH while coring.
363 | Core 12FB | Core 8,073 ft to 8,083 ft. | 1 | 475.75 | 234:45 | 235:45 | Helix/Geotek.
364 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 476.5 | 235:45 | 236:30 | Slb/Geotek/Helix. Rotate and manipulate as required.
365 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 476.75 | 236:30 | 236:45 | Helix/Geotek/Slb.
366 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 477 | 236:45 | 237:00 | Helix/Geotek/Slb.
367 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 477.5 | 237:00 | 237:30 | Geotek/Helix.
368 |  | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.25 | 477.75 | 237:30 | 237:45 | Geotek/Helix.
369 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, land PCTB on drill pipe. | 0.5 | 478.25 | 237:45 | 238:15 | Geotek/Helix.
370 |  | Change out wireline pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 479 | 238:15 | 239:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
371 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 479.75 | 239:00 | 239:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
372 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 480 | 239:45 | 240:00 | Helix/Geotek/Slb.
2017-05-19
373 | Safety | Operations safety meeting. | 0.5 | 480.5 | 240:00 | 240:30
374 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 480.5 | 240:30 | 240:30 | Slb. RIH while coring.
375 | Core 13FB | Core 8,083 ft to 8,093 ft. | 1 | 481.5 | 240:30 | 241:30
376 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 482.25 | 241:30 | 242:15 | Slb/Geotek/Helix. Rotate and manipulate as required.
377 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 482.5 | 242:15 | 242:30 | Helix/Geotek/Slb.
378 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 482.75 | 242:30 | 242:45 | Helix/Geotek/Slb.
379 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 483.25 | 242:45 | 243:15 | Geotek/Helix.
380 | Hole Cleaning (if required) | Pick up center bit w/tugger, load/land center bit on drill pipe. | 0.25 | 483.5 | 243:15 | 243:30
381 |  | Latch wireline to center bit, close drill string, RIH w/center bit on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 484.25 | 243:30 | 244:15 | Helix/Slb/Geotek. Rotate and manipulate as required.
382 |  | Land/latch center bit in outer core barrel assy, maintain circulation at 10 gpm min. | 0.75 | 485 | 244:15 | 245:00 | Helix/Slb/Geotek. Rotate and manipulate as required.
383 |  | POOH w/wireline @ max safe speed, maintain circulation at 10 gpm min. | 0 | 485 | 245:00 | 245:00 | Helix/Slb/Geotek. POOH whole cleaning hole.
384 |  | Break drill string, change out wireline running tool for emergency pulling tool, close drill string. | 0.25 | 485.25 | 245:00 | 245:15
385 |  | RIH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0 | 485.25 | 245:15 | 245:15 | RIH while cleaning hole.
386 |  | Hole cleaning. | 1.5 | 486.75 | 245:15 | 246:45
387 |  | Latch center bit, POOH w/center bit on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 487.5 | 246:45 | 247:30 | Helix/Slb/Geotek. Rotate and manipulate as required.
388 |  | Break drill string, install lifting clamp on center bit, land center bit on drill pipe, unlatch wireline, lay out center bit w/tugger. | 0.25 | 487.75 | 247:30 | 247:45 | Helix/Slb/Geotek. Rotate and manipulate as required.
389 | Coring | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.25 | 488 | 247:45 | 248:00 | Geotek/Helix.
390 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, transfer and land PCTB assy on drill pipe. | 0.5 | 488.5 | 248:00 | 248:30 | Geotek/Helix.
391 |  | Change out wireline emergency pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 489.5 | 248:30 | 249:30 | Slb/Geotek/Helix. Rotate and manipulate as required.
392 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 490.25 | 249:30 | 250:15 | Slb/Geotek/Helix. Rotate and manipulate as required.
393 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 490.5 | 250:15 | 250:30 | Helix/Geotek/Slb.
394 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 490.5 | 250:30 | 250:30 | Slb. RIH while coring.
395 | Core 14FB | Core 8,093 ft to 8,103 ft. | 1 | 491.5 | 250:30 | 251:30
396 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.5 | 492 | 251:30 | 252:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
397 | Safety | Operations safety meeting. | 0.5 | 492.5 | 252:00 | 252:30
398 |  | Continue POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 493.25 | 252:30 | 253:15 | Slb/Geotek/Helix. Rotate and manipulate as required.
399 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 493.5 | 253:15 | 253:30 | Helix/Geotek/Slb.
400 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 493.75 | 253:30 | 253:45 | Helix/Geotek/Slb.
401 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 494.25 | 253:45 | 254:15 | Geotek/Helix.
402 |  | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.25 | 494.5 | 254:15 | 254:30 | Geotek/Helix.
403 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, land PCTB on drill pipe. | 0.5 | 495 | 254:30 | 255:00 | Geotek/Helix.
404 |  | Change out wireline pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 496 | 255:00 | 256:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
405 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 496.75 | 256:00 | 256:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
406 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 497 | 256:45 | 257:00 | Helix/Geotek/Slb.
407 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 497 | 257:00 | 257:00 | Slb. RIH while coring.
408 | Core 15FB | Core 8,103 ft to 8,113 ft. | 1 | 498 | 257:00 | 258:00
409 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 498.75 | 258:00 | 258:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
410 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 499 | 258:45 | 259:00 | Helix/Geotek/Slb.
411 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 499.25 | 259:00 | 259:15 | Helix/Geotek/Slb.
412 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 499.75 | 259:15 | 259:45 | Geotek/Helix.
413 |  | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.25 | 500 | 259:45 | 260:00 | Geotek/Helix.
414 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, land PCTB on drill pipe. | 0.5 | 500.5 | 260:00 | 260:30 | Geotek/Helix.
415 |  | Change out wireline pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 501.5 | 260:30 | 261:30 | Slb/Geotek/Helix. Rotate and manipulate as required.
416 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 502.25 | 261:30 | 262:15 | Slb/Geotek/Helix. Rotate and manipulate as required.
417 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 502.5 | 262:15 | 262:30 | Helix/Geotek/Slb.
418 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 502.5 | 262:30 | 262:30 | Slb. RIH while coring.
419 | Core 16FB | Core 8,113 ft to 8,123 ft. | 1 | 503.5 | 262:30 | 263:30
420 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.5 | 504 | 263:30 | 264:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
2017-05-20
421 | Safety | Operations safety meeting. | 0.5 | 504.5 | 264:00 | 264:30
422 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 504.75 | 264:30 | 264:45 | Helix/Geotek/Slb.
423 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 505 | 264:45 | 265:00 | Helix/Geotek/Slb.
424 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 505.5 | 265:00 | 265:30 | Geotek/Helix.
425 | Drilling | Pick up center bit w/tugger, load/land center bit in drill pipe. | 0.25 | 505.75 | 265:30 | 265:45 | Helix/Slb/Geotek. Rotate and manipulate as required.
426 |  | Change out wireline pulling tool for running tool, latch wireline to center bit, pick up center bit, remove lifting clamp, close drill string, RIH w/center bit on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 506.5 | 265:45 | 266:30 | Helix/Slb/Geotek. Rotate and manipulate as required.
427 |  | Land/latch center bit in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 507.25 | 266:30 | 267:15 | Helix/Slb/Geotek. Rotate and manipulate as required.
428 | Drilling | Drill from 8,123 ft to 8,149 ft. | 1 | 508.25 | 267:15 | 268:15
429 | Hole Cleaning | Clean hole. | 1 | 509.25 | 268:15 | 269:15
430 |  | Break drill string, change out wireline running tool for emergency pulling tool, close drill string, RIH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 510 | 269:15 | 270:00
431 |  | Latch center bit, POOH w/center bit on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 510.75 | 270:00 | 270:45 | Helix/Slb/Geotek. Rotate and manipulate as required.
432 |  | Break drill string, install lifting clamp on center bit, land center bit on drill pipe, unlatch wireline. | 0.25 | 511 | 270:45 | 271:00 | Helix/Slb/Geotek. Rotate and manipulate as required.
433 |  | Lay out center bit w/tugger. | 0.25 | 511.25 | 271:00 | 271:15
434 | Coring | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.25 | 511.5 | 271:15 | 271:30 | Geotek/Helix.
435 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, transfer and land PCTB assy on drill pipe. | 0.5 | 512 | 271:30 | 272:00 | Geotek/Helix.
436 |  | Change out wireline emergency pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 513 | 272:00 | 273:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
437 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 513.75 | 273:00 | 273:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
438 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 514 | 273:45 | 274:00 | Helix/Geotek/Slb.
439 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 514 | 274:00 | 274:00 | Slb. RIH while coring.
440 | Core 17FB | Core 8,149 ft to 8,159 ft. | 1 | 515 | 274:00 | 275:00
441 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 515.75 | 275:00 | 275:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
442 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 516 | 275:45 | 276:00 | Helix/Geotek/Slb.
443 | Safety | Operations safety meeting. | 0.5 | 516.5 | 276:00 | 276:30
444 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 516.75 | 276:30 | 276:45 | Helix/Geotek/Slb.
445 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 517.25 | 276:45 | 277:15 | Geotek/Helix.
446 |  | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.25 | 517.5 | 277:15 | 277:30 | Geotek/Helix.
447 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, land PCTB on drill pipe. | 0.5 | 518 | 277:30 | 278:00 | Geotek/Helix.
448 |  | Change out wireline pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 519 | 278:00 | 279:00 | Slb/Geotek/Helix. Rotate and manipulate as required.
449 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 519.75 | 279:00 | 279:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
450 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 520 | 279:45 | 280:00 | Helix/Geotek/Slb.
451 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 520 | 280:00 | 280:00 | Slb. RIH while coring.
452 | Core 18FB | Core 8,159 ft to 8,169 ft. | 1 | 521 | 280:00 | 281:00
453 |  | Lower wireline, latch PCTB. | 0.5 | 521.5 | 281:00 | 281:30 | Slb/Geotek/Helix. Rotate and manipulate as required.
454 |  | POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.25 | 521.75 | 281:30 | 281:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
455 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 522 | 281:45 | 282:00 | Helix/Geotek/Slb.
456 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 522.25 | 282:00 | 282:15 | Helix/Geotek/Slb.
457 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 522.75 | 282:15 | 282:45 | Geotek/Helix.
458 |  | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.25 | 523 | 282:45 | 283:00 | Geotek/Helix.
459 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, land PCTB on drill pipe. | 0.5 | 523.5 | 283:00 | 283:30 | Geotek/Helix.
460 |  | Change out wireline pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 524.5 | 283:30 | 284:30 | Slb/Geotek/Helix. Rotate and manipulate as required.
461 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 525.25 | 284:30 | 285:15 | Slb/Geotek/Helix. Rotate and manipulate as required.
462 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 525.5 | 285:15 | 285:30 | Helix/Geotek/Slb.
463 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 525.5 | 285:30 | 285:30 | Slb. RIH while coring.
464 | Core 19FB | Core 8,169 ft to 8,179 ft. | 1 | 526.5 | 285:30 | 286:30
465 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 527.25 | 286:30 | 287:15 | Slb/Geotek/Helix. Rotate and manipulate as required.
466 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 527.5 | 287:15 | 287:30 | Helix/Geotek/Slb.
467 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.5 | 528 | 287:30 | 288:00 | Helix/Geotek/Slb.
2017-05-21
468 | Safety | Operations safety meeting. | 0.5 | 528.5 | 288:00 | 288:30
469 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 529 | 288:30 | 289:00 | Geotek/Helix.
470 |  | Pick up refurbished PCTB lower end w/tugger, load/land on assembly stand over 10" mousehole. | 0.25 | 529.25 | 289:00 | 289:15 | Geotek/Helix.
471 |  | Pick up PCTB upper end w/tugger, make up to PCTB lower end, pick up PCTB assy, remove lifting clamp from lower end, land PCTB on drill pipe. | 0.5 | 529.75 | 289:15 | 289:45 | Geotek/Helix.
472 |  | Change out wireline pulling tool for running tool, latch wireline to PCTB, pick up PCTB w/wireline, remove lifting clamp, close drill string, RIH w/PCTB on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 530.75 | 289:45 | 290:45 | Slb/Geotek/Helix. Rotate and manipulate as required.
473 |  | Land/latch PCTB in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 531.5 | 290:45 | 291:30 | Slb/Geotek/Helix. Rotate and manipulate as required.
474 |  | Break drill string, change out wireline running tool for pulling tool, close drill string. | 0.25 | 531.75 | 291:30 | 291:45 | Helix/Geotek/Slb.
475 |  | RIH w/wireline at max safe speed to 7,950 ft. | 0 | 531.75 | 291:45 | 291:45 | Slb. RIH while coring.
476 | Core 20FB | Core 8,179 ft to 8,189 ft. | 1 | 532.75 | 291:45 | 292:45 | Bottom of hydrate @ 8,166 ft RKB (1,445 fbsf).
477 |  | Lower wireline, latch PCTB, POOH w/PCTB at max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 533.5 | 292:45 | 293:30 | Slb/Geotek/Helix. Rotate and manipulate as required.
478 |  | Break drill string, install lifting clamp on PCTB upper end, land PCTB on drill string, unlatch wireline. | 0.25 | 533.75 | 293:30 | 293:45 | Helix/Geotek/Slb.
479 |  | Pick up PCTB w/tugger, install lifting clamp on lower end, load/land lower end in cold shuck. | 0.25 | 534 | 293:45 | 294:00 | Helix/Geotek/Slb.
480 |  | Break PCTB upper end, stage in mousehole. | 0.5 | 534.5 | 294:00 | 294:30 | Geotek/Helix.
481 | Hole Survey (Gyro Tool) | Pick up survey tool w/tugger, load/land in drill pipe, latch wireline to survey tool, close drill pipe. | 0.5 | 535 | 294:30 | 295:00 | Rotate and circulate as required.
482 |  | RIH w/survey tool to 6,670 ft @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 535.75 | 295:00 | 295:45 | Rotate and circulate as required.
483 |  | RIH w/survey tool to 7,600 ft @ 200 ft/min, maintain circulation @ 10 gpm min. | 0.25 | 536 | 295:45 | 296:00
484 |  | Stop at 7,600 ft for 5 min. | 0 | 536 | 296:00 | 296:00
485 |  | RIH w/survey tool to 8,182 ft (TD) @ 200 ft/min, maintain circulation @ 10 gpm min. | 0.25 | 536.25 | 296:00 | 296:15
486 |  | Stop at 8,182 (TD) for 5 min. | 0 | 536.25 | 296:15 | 296:15
487 |  | POOH w/survey tool to 7,600 ft @ 200 ft/min, maintain circulation @ 10 gpm min. | 0.5 | 536.75 | 296:15 | 296:45 | Rotate and circulate as required.
488 |  | Stop at 7,600 ft for 5 min. | 0 | 536.75 | 296:45 | 296:45
489 |  | POOH w/survey tool @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 537.5 | 296:45 | 297:30 | Rotate and circulate as required.
490 |  | Break drill pipe, lay out survey tool. | 0.5 | 538 | 297:30 | 298:00
491 | Cementing | Rig down wireline. | 1 | 539 | 298:00 | 299:00
492 |  | Displace hole from TD to 7,900 ft with 11.5 ppg Hi- Vis pad mud. | 1 | 540 | 299:00 | 300:00
493 | Safety | Operations safety meeting. | 0.5 | 540.5 | 300:00 | 300:30
494 |  | POOH to 7,900 ft. | 0.75 | 541.25 | 300:30 | 301:15 | Bit at top of pad mud, 100 ft above hydrate zone.
495 |  | Drop cementing liner. | 0.25 | 541.5 | 301:15 | 301:30 | Free fall deploy.
496 |  | Rig up cementing manifold. | 1.5 | 543 | 301:30 | 303:00
497 |  | Pump cement per Schlumberger program. | 5.5 | 548.5 | 303:00 | 308:30 | 300 ft plug.
498 |  | Rig down cementing manifold. | 1.5 | 550 | 308:30 | 310:00
499 |  | POOH to 6625 ft (100 ft above seafloor). | 2 | 552 | 310:00 | 312:00 | 100 ft above sea floor. Pull slowly through cement column 5 min/double.
2017-05-22
500 | Safety | Operations safety meeting. | 0.5 | 552.5 | 312:00 | 312:30
501 |  | Circulate ≥2X drill string volume w/sea water and 3x rubber balls at ≥5 bbl/min. | 1.5 | 554 | 312:30 | 314:00 | Pump foam pipe wipers.
502 |  | Rig up wireline. | 1 | 555 | 314:00 | 315:00 | Rig up while circulating.
503 |  | RIH w/wireline, latch OCBA cementing liner. | 0 | 555 | 315:00 | 315:00 | Circulate. RIH while circulating.
504 |  | POOH with cementing liner. | 0.75 | 555.75 | 315:00 | 315:45 | Circulate.
505 |  | Break drill string, lay out cementing liner. | 0.25 | 556 | 315:45 | 316:00
506 |  | Circulate ≥1X drill string volume w/sea water and pipe wipers at ≥5 bbl/min. | 1 | 557 | 316:00 | 317:00 | Pump foam pipe wipers.
507 |  | Observe borehole for signs of out flow. | 0 | 557 | 317:00 | 317:00 | Observe while cleaning drill string.
508 | Tag Cement | Break drill string, pick up center bit w/tugger, load/land center bit in drill pipe. | 0.25 | 557.25 | 317:00 | 317:15 | Helix/Slb/Geotek. Rotate and manipulate as required.
509 |  | Change out wireline pulling tool for running tool, latch wireline to center bit, pick up center bit, remove lifting clamp, close drill string, RIH w/center bit on wireline @ max safe speed, maintain circulation @ 10 gpm min. | 1 | 558.25 | 317:15 | 318:15 | Helix/Slb/Geotek. Rotate and manipulate as required.
510 |  | Land/latch center bit in outer core barrel assy, POOH w/wireline @ max safe speed, maintain circulation @ 10 gpm min. | 0.75 | 559 | 318:15 | 319:00 | Helix/Slb/Geotek. Rotate and manipulate as required.
511 |  | Rig down wireline. | 1 | 560 | 319:00 | 320:00
512 |  | Reenter Hole H-005 | 1 | 561 | 320:00 | 321:00
513 |  | RIH to 7600 ft (top of cement), set 15,000 WOB on cement. | 2 | 563 | 321:00 | 323:00 | Rotate only enough to monitor torque.
514 |  | POOH to 6564 ft (100 ft above seafloor) | 1 | 564 | 323:00 | 324:00
515 | Safety | Operations safety meeting. | 0.5 | 564.5 | 324:00 | 324:30
516 |  | Continue POOH to 6564 ft (100 ft above seafloor) | 1 | 565.5 | 324:30 | 325:30
517 |  | Rig up wireline. | 1 | 566.5 | 325:30 | 326:30 | If pipe is draining fast enough to not have to pull a wet string center bit can be left in place.
518 |  | RIH w/pulling tool at max safe speed. | 0.5 | 567 | 326:30 | 327:00
519 |  | Latch center bit, POOH w/center bit on wireline @ max safe speed. | 0.5 | 567.5 | 327:00 | 327:30
520 |  | Break drill string, lay out center bit. | 0.25 | 567.75 | 327:30 | 327:45
521 |  | Rig down wireline. | 1 | 568.75 | 327:45 | 328:45
522 |  | Rack top drive. | 0.5 | 569.25 | 328:45 | 329:15
523 |  | POOH to top of outer core barrel assy. | 6.75 | 576 | 329:15 | 336:00
2017-05-23
524 | Safety | Operations safety meeting. | 0.5 | 576.5 | 336:00 | 336:30
525 |  | Continue POOH to top of outer core barrel assy. | 1.25 | 577.75 | 336:30 | 337:45
526 |  | Break down and layout outer core barrel assy. | 2.5 | 580.25 | 337:45 | 340:15 | Clean, re-dope, and install thread protectors, all sub and collar threads.
527 |  | Clear rig floor for demobilization. | 2.5 | 582.75 | 340:15 | 342:45
528 |  | ROV site survey. | 1 | 583.75 | 342:45 | 343:45 | Complete while POOH with BHA.
529 |  | Recover ROV, beacon(s). | 1 | 584.75 | 343:45 | 344:45 | Complete while POOH with BHA.
530 |  | Begin demobilization. | 15.25 | 600 | 344:45 | 360:00
2017-05-24
531 |  | Demobilization. Pack and off load all containers and equipment. | 24 | 624 | 360:00 | 384:00
2017-05-25
532 |  | Demobilization. Pack and off load all containers and equipment. | 24 | 648 | 384:00 | 408:00
533 |  | Disembark Geotek and UT personnel via helicopter. |  |  |  |  | One Geotek person to accompany core samples on work boat.
Notes:
1 | Time estimate assumes worst case and includes gyro survey at 1,000 fbsf and cementing in both holes.
2 | Site GC-955, water depth = 6,670 fbsl, RKB to sea level = 51 ft
3 | 10 pressurized core samples per hole to be taken
4 | Instrumented PCTB assembled for deployment
5 | Rig capable of handling doubles
6 | All depths are referenced to RKB (rig floor).
7 | Plug and abandon cementing per Schlumberger program
8 | MU = make up
9 | POOH = pull out of hole
10 | RIH - run in hole
11 | Core depths shown are place holders, actual depths to be determined
12 | Cementing depths are place holders, actual depths to be determined

## Flow Chart Mob - Hole A
Hole A Activity Forecast Flow Chart
Revision: D 18 April 2017
Day | 2017-04-25 | 2017-04-26 | 2017-04-27 | 2017-04-28 | 2017-04-29 | 2017-04-30 | 2017-05-01 | 2017-05-02 | 2017-05-03 | 2017-05-04 | 2017-05-05 | 2017-05-06 | 2017-05-07 | 2017-05-08 | 2017-05-09 | 2017-05-10 | 2017-05-11
In Port
Transit
FMEA Seatrial
Mobilization (on Site)
MU Cutting Shoe BHA
Flow Test #1
RIH Hole A
Spud Hole A & 1,000 ft Survey
Core 1CS
Core 2CS
Core 3CS
Drilling & Hole Cleaning
Core 4CS
Core 5CS
Core 6CS
Drilling & Hole Cleaning
Core 7CS
Core 8CS
Core 9CS
Core 10CS
Drill Logging Rat Hole
Logging
Cementing
POOH Hole A

## Flow Chart Hole B - Demob
Hole B Activity Forecast Flow Chart
Revision: D 18 April 2017
Day | 2017-05-11 | 2017-05-12 | 2017-05-13 | 2017-05-14 | 2017-05-15 | 2017-05-16 | 2017-05-17 | 2017-05-18 | 2017-05-19 | 2017-05-20 | 2017-05-21 | 2017-05-22 | 2017-05-23 | 2017-05-24
MU Face Bit BHA
Flow Test #1
RIH Hole B
Spud Hole B & 1,000 ft Survey
Core 11FB
Core 12FB
Core 13FB
Drilling & Hole Cleaning
Core 14FB
Core 15FB
Core 16FB
Drilling & Hole Cleaning
Core 17FB
Core 18FB
Core 19FB
Core 20FB
Survey
Cementing
POOH Hole B
Demob

## Cementing Hole A
UT/DOE PCTB Marine Test Activity Forecast and Time Estimate
Cementing Hole A - Normal Plug and Abandon
Revision: C Date: 28 February 2017
ITEM | ACTIVITY | TASK DESCRIPTION | TIME |  |  |  | NOTES
|  |  | (hr) | CUM | Start | Stop
1 | Cementing Hole A | RIH to TD ((8,420 ft RKB) (1,699 fbsf)) | 1 | 1 | 0:00 | 1:00
2 |  | Displace hole from TD to 7,900 ft (1,178 fbsf) with 11.5 ppg Hi- Vis pad mud. | 1 | 2 | 1:00 | 2:00
3 |  | POOH to 7,900 ft (1,178 fbsf) | 0.75 | 2.75 | 2:00 | 2:45 | Bit at top of pad mud, 100 ft above hydrate zone.
4 |  | Drop dummy core barrel | 0.5 | 3.25 | 2:45 | 3:15 | Free fall deploy.
5 |  | Pump cement per Schlumberger program | 5 | 8.25 | 3:15 | 8:15 | 300 ft plug.
6 |  | POOH to 6,570 ft RKB | 1.25 | 9.5 | 8:15 | 9:30 | 100 ft above sea floor. Pull slowly through cement column.
7 |  | Circulate 2X drill string volume w/sea water | 1.5 | 11 | 9:30 | 11:00 | Pump foam pipe wipers.
8 |  | Rig up wireline | 0.5 | 11.5 | 11:00 | 11:30
9 |  | RIH w/wireline, POOH with dummy core barrel | 1.75 | 13.25 | 11:30 | 13:15 | Circulate.
10 |  | Rig down wireline | 0.5 | 13.75 | 13:15 | 13:45
11 |  | Circulate 2X drill string volume w/sea water and pipe wipers | 0.75 | 14.5 | 13:45 | 14:30 | Pump foam pipe wipers
12 |  | Observe borehole for signs of out flow | 0 | 14.5 | 14:30 | 14:30 | Observe while cleaning drill string

## Cementing Hole B
UT/DOE PCTB Marine Test Activity Forecast and Time Estimate
Cementing Hole B - Normal Plug and Abandon
Revision: C Date: 28 February 2017
ITEM | ACTIVITY | TASK DESCRIPTION | TIME |  |  |  | NOTES
|  |  | (hr) | CUM | Start | Stop
1 | Cementing Hole B | Displace hole from TD to 7,900 ft (1,178 fbsf) with 11.5 ppg Hi- Vis pad mud. | 1 | 1 | 0:00 | 1:00
2 |  | POOH to 7,900 ft (1,178 fbsf). | 0.75 | 1.75 | 1:00 | 1:45 | Bit at top of pad mud, 100 ft above hydrate zone.
3 |  | Drop dummy core barrel. | 0.5 | 2.25 | 1:45 | 2:15 | Free fall deploy.
4 |  | Pump cement per Schlumberger program. | 5 | 7.25 | 2:15 | 7:15 | 300 ft plug.
5 |  | POOH to 6,570 ft RKB. | 1.25 | 8.5 | 7:15 | 8:30 | 100 ft above sea floor. Pull slowly through cement column.
6 |  | Circulate 2X drill string volume w/sea water. | 1.5 | 10 | 8:30 | 10:00 | Pump foam pipe wipers.
7 |  | Rig up wireline. | 0.5 | 10.5 | 10:00 | 10:30
8 |  | RIH w/wireline, POOH with dummy core barrel. | 1.75 | 12.25 | 10:30 | 12:15 | Circulate.
9 |  | Rig down wireline. | 0.5 | 12.75 | 12:15 | 12:45
10 |  | Circulate 2X drill string volume w/sea water and pipe wipers. | 0.75 | 13.5 | 12:45 | 13:30 | Pump foam pipe wipers.
11 |  | Observe borehole for signs of out flow. | 0 | 13.5 | 13:30 | 13:30 | Observe while cleaning drill string.

## Log Tool Drift Test t-est
UT/DOE PCTB Marine Test Logging Tool Drift Test Time Estimate
Revision: B Date: 1 November 2016
ITEM | ACTIVITY | TASK DESCRIPTION | TIME |  |  |  | NOTES
|  |  | (hr) | CUM | Start | Stop
1 | Logging | RIH 3 stands (doubles) and hang off at rig floor | 0.75 | 0.75 | 0:00 | 0:45
2 | Tool | Swap winch drums | 1 | 1.75 | 0:00 | 1:00
3 | Drift | Rig up logging line | 3 | 4.75 | 0:45 | 3:45
4 | Test | Assemble logging tools | 0.75 | 5.5 | 3:45 | 4:30
5 |  | RIH, drift test, POOH | 1 | 6.5 | 4:30 | 5:30
6 |  | LO logging tools | 0.75 | 7.25 | 5:30 | 6:15
7 |  | Rig down logging line | 3 | 10.25 | 5:30 | 8:30
8 |  | Swap winch drums | 1 | 11.25 | 6:15 | 7:15